## README
AudioForge — notation, interop and musical-analysis roadmap (engine 3.1 line)
Generated by Claude Fable 5.1 via Claude Code on 2026-09-06. Disclaimer: no information in this workbook should be taken for granted; any statement not backed by a verifiable reference may be invalid, erroneous, or a hallucination. Statuses derive from docs/evolution/harness-notation.md §4 (T0) and advance only from evidence bundles under docs/evolution/evidence-notation/.
Companion files | docs/evolution/report-notation.md · docs/evolution/harness-notation.md
Baseline | T0 = 2026-09-06 on branch release/engine-3.0.0 (16b2cc2), oracles in a scratch venv: music21 10.5.0, LilyPond 2.25.12 wheel, MusicXML 3.1 XSD
ID conventions | RN-<ws>-<nnn> roadmap items (ws: O oracles/gate, X export, I import, T tuning, A analysis, P proof sheet/engraving, D docs/contract, Q performance) · HARNESS-N<CAT>-<nnn> assertions · M0…M6 = checkpoints T0…T6 · NREQ-n report requirements
Status vocabulary | not-started · in-progress · complete (acceptance criteria met and harness rows PASS in an evidence bundle) · blocked · parked (outside this plan's T6)
Completion rule | implementation exists; harness tests execute; acceptance criteria pass; evidence exists; milestone gate accepts. 'Done because code was written' is not a state.
Critical path | RN-O-001 → RN-O-002 → RN-X-001 → RN-X-005 → RN-I-001 → RN-I-002 → RN-O-003 (parity green) → RN-X-010 → RN-T-002 → release (D2).
Day 1 | RN-O-001, RN-O-002, RN-O-005, RN-T-001, RN-P-001, RN-D-002, RN-D-003, RN-D-004, RN-D-005
Out of scope | Track M musicology beyond chord identity (AF-M02, M03, M04, M06, M07), JI/temperaments/Scala (RN-T-004 parked), in-house engraving, vocal rendering.
Sheets | Executive Roadmap · Detailed Backlog · Dependencies · Milestones · Harness Coverage · Risks · Resources · Traceability · Decisions

## Executive Roadmap
Milestone | Checkpoint | Name | Objective | Roadmap items | Critical-path items | Exit gate (harness) | Unlocks | Status
M0 | T0 | Baseline | Measure the notation, interop and analysis surface against external oracles | — | — | 53 assertions executed; §4 of harness-notation.md | M1 | complete (2026-09-06)
M1 | T1 | Honesty and oracles | Say what the surface is, and make the oracles part of the toolchain: `oracles` dev extra, vendored XSD, fixture corpus, runner, ADR-0011, proof-sheet labelling, interim tuning diagnostic | RN-O-001, RN-O-002, RN-O-003, RN-O-005, RN-T-001, RN-P-001, RN-D-002, RN-D-003, RN-D-004, RN-D-005 | RN-O-001, RN-O-002, RN-O-003 | HARNESS-NORA-001/002/003, NGATE-001, NENG-003, NTUN-003, NDOC-005 PASS | M2 | complete (T3 evidence)
M2 | T2 | Interchange core | Notated export derives structure from the spec (meter unit, bar length, key and tempo changes, pickup); chords and parts in both exporters; multi-part, chord-aware import | RN-X-001, RN-X-002, RN-X-003, RN-X-004, RN-X-005, RN-I-001, RN-I-002, RN-I-003 | RN-X-001, RN-X-005, RN-I-001, RN-I-002 | HARNESS-NXML-002…005, NXML-009, NIMP-001…003, NMIDI-002/003 PASS | M3 | complete (T3 evidence)
M3 | T3 | Oracle integration | music21 and LilyPond parity green on the fixture corpus; expressive notation projected; generated coverage matrix and manifest entries | RN-O-003, RN-X-006, RN-X-007, RN-X-008, RN-X-009, RN-X-010, RN-I-004, RN-I-005, RN-A-001, RN-D-001 | RN-O-003, RN-X-010 | HARNESS-NXML-001, NXML-006…008, NXML-010/011, NIMP-004/005, NSEM-001/002, NDOC-001/002, NANA-001/002 PASS | M4 | complete (T3 evidence)
M4 | T4 | Tuning activation | The `tuning:` directive drives the render (n-EDO slice) with FFT proof; default path byte-identical; microtonal interop documented | RN-T-002, RN-T-003 | RN-T-002 | HARNESS-NTUN-001/002/004 PASS; goldens unchanged | M5 | not-started
M5 | T5 | Hardening | Perf budgets, glyph fix, optional LilyPond engraving backend, corpus round trips, CI oracle job when Actions execute | RN-O-004, RN-A-002, RN-P-002, RN-P-003, RN-Q-001 | — | HARNESS-NPERF-001…004, NENG-002/004, NANA-004, NORA-004 PASS or waived | M6 | not-started
M6 | T6 | Desired state | Engine 3.1.0 / DSL 2.1: notation surface honest, interchange oracle-verified, tuning real; all non-waived rows PASS | RN-T-004 | — | every HARNESS-N row PASS except live waivers; README/INTEROP/manifest agree; release gate | — | not-started

## Detailed Backlog
ID | Workstream | Epic | Milestone | Deliverable | Description | Current State | Target State | Priority | Dependency IDs | Dependency Type | Blocks | Can Run in Parallel | Independent / Dependent | Critical Path | Owner / Required Role | Required Environment | Required Infrastructure | Required Permissions | Required API Keys / Credentials | Estimated Effort | Risk | Acceptance Criteria | Harness Test IDs | Exit Gate | Status | Progress % | Evidence / Artifact | Notes | Day 1 | Why does this exist? | What does it unlock?
RN-D-002 | D Docs & contract | EP-N3 Honest contract | M1 | README section 'Notation and analysis': semantic score fields, proof sheet, MusicXML/MIDI interchange to LilyPond and music21, what is not attempted | T0: README has no mention of score, notation or MusicXML. | silent | HARNESS-NDOC-003 PASS | P1 | RN-D-004 | soft | — | yes | independent | no | maintainer | reference | — | push | none | XS | none | section present; test_docs_regression guard | HARNESS-NDOC-003 | M1 | complete | 100 | docs/evolution/evidence-notation/T3/results.json; HARNESS-NDOC-003 | Day 1 | yes | Users find the score verb only by reading argparse. | —
RN-D-003 | D Docs & contract | EP-N3 Honest contract | M1 | DSL_GAP_SPEC G6 corrected: tuning metadata accepted but inert until RN-T-002; G8 'closed' qualified by the T0 import findings |  | G6/G8 say closed | HARNESS-NDOC-004 PASS | P1 | — | — | — | yes | independent | no | maintainer | reference | — | push | none | XS | none | text states the limits with harness IDs | HARNESS-NDOC-004 | M1 honesty gate | complete | 100 | docs/evolution/evidence-notation/T3/results.json; HARNESS-NDOC-004 | Day 1 | yes | A gap spec that says closed while the directive is inert misleads agents. | —
RN-D-004 | D Docs & contract | EP-N3 Honest contract | M1 | ADR-0011: notation positioning — semantic score contract + oracle-verified interchange; engraving and deep musicology delegated to LilyPond and music21; proof sheet retained |  | no record | HARNESS-NDOC-005 PASS | P0 | — | — | RN-D-002, RN-A-003 | yes | independent | no | maintainer | reference | — | push | none | XS | none | ADR accepted; test_docs_site sections | HARNESS-NDOC-005 | M1 | complete | 100 | docs/evolution/evidence-notation/T3/results.json; HARNESS-NDOC-005 | Day 1 | yes | The AF-R12 rule: a public-surface positioning is a decision. | docs
RN-D-005 | D Docs & contract | EP-N3 Honest contract | M1 | Backlog items BL-045+ registering this plan (epic + export, import, tuning slice, oracles) with evidence checks |  | not registered | HARNESS-NGATE-006 PASS | P1 | — | — | — | yes | independent | no | maintainer | reference | node | push | none | XS | none | governance script green | HARNESS-NGATE-006 | M1 | complete | 100 | docs/evolution/evidence-notation/T3/results.json; HARNESS-NGATE-006 | Day 1 | yes | The registry is the system of record. | —
RN-O-001 | O Oracles & gate | EP-N2 Oracle-verified interchange | M1 | `oracles` dev extra (music21, lilypond wheel, xmlschema) + vendored MusicXML 3.1 XSD under tests/fixtures/musicxml/xsd with its W3C licence notice | At T0 the oracles exist only in a scratch venv built by hand; nothing in the repository can run them. | No extra; no XSD in tree | `uv pip install -e '.[oracles]'` yields working music21, lilypond and xmlschema; XSD validation runs offline | P0 | — | — | RN-O-003, RN-O-004, RN-O-005, every NXML/NIMP oracle row | yes | independent | yes | maintainer | reference | network once (wheels ~60 MB) | push | none | S | RN1 dependency weight; RN2 XSD licence | HARNESS-NORA-001, NORA-002 PASS | HARNESS-NORA-001, HARNESS-NORA-002 | M1 | complete | 100 | docs/evolution/evidence-notation/T3/results.json; HARNESS-NORA-001, HARNESS-NORA-002 | Day 1 | yes | Verification against the tools the surface is measured against cannot depend on a hand-built venv. | all oracle-backed assertions
RN-O-002 | O Oracles & gate | EP-N2 Oracle-verified interchange | M1 | Fixture corpus tests/fixtures/notation/*.af (≥ 8 specs) with expected-features JSON: meter units (3/4, 7/8, 6/8), pickup, key and tempo changes, chords, ties across bars, polymeter, dynamics and articulations, tuplets and lyrics | T0 measured two ad-hoc specs and one gitignored composition; the harness needs a committed corpus. | No corpus | HARNESS-NGATE-001 PASS | P0 | — | — | RN-O-003, RN-X-*, RN-I-* | yes | independent | yes | maintainer | reference | — | push | none | S | none | each fixture compiles; expected-features JSON lists constructs present | HARNESS-NGATE-001 | M1 | complete | 100 | docs/evolution/evidence-notation/T3/results.json; HARNESS-NGATE-001 | Day 1 | yes | Parity tests need a stable, versioned input set. | oracle tests
RN-O-003 | O Oracles & gate | EP-N2 Oracle-verified interchange | M1 (skeleton) → M3 (green) | tests/test_notation_oracles.py: XSD validity, music21 parity (parts, measures, time/key signatures, pitch multisets, durations), LilyPond zero-warning engraving, chord-root parity; skips loudly without the extra; `make oracle-check` target | Turns the T0 hand measurements into standing assertions. | No oracle tests | HARNESS-NORA-003 PASS; NXML-001/010, NENG-001, NANA-001 measured by tests | P0 | RN-O-001, RN-O-002 | hard | RN-O-004 | yes | dependent | yes | maintainer | reference + oracles | — | push | none | M | RN5 oracle version drift | tests pass with the extra; skip with a printed reason without it | HARNESS-NORA-003, HARNESS-NXML-001, HARNESS-NXML-010, HARNESS-NENG-001, HARNESS-NANA-001, HARNESS-NGATE-002, HARNESS-NGATE-003, HARNESS-NGATE-004, HARNESS-NANA-003, HARNESS-NMIDI-001 | M1 skeleton; M3 green | complete | 100 | docs/evolution/evidence-notation/T3/results.json; HARNESS-NORA-003, HARNESS-NXML-001, HARNESS-NXML-010, HARNESS-NENG-001, HARNESS-NANA-001, HARNESS-NGATE-002, HARNESS-NGATE-003, HARNESS-NGATE-004, HARNESS-NANA-003, HARNESS-NMIDI-001 |  | no | A measurement nobody re-runs is an anecdote. | objective interchange gate
RN-O-005 | O Oracles & gate | EP-N2 Oracle-verified interchange | M1 | `scripts/harness-notation.sh` (from harness-notation.md §8) writing docs/evolution/evidence-notation/<checkpoint>/ | Same runner discipline as the release harness, separate evidence root. | Runner exists as a code block | HARNESS-NGATE-005 PASS | P1 | RN-O-001 | soft | checkpoint sign-offs | yes | dependent | no | maintainer | reference | — | push | none | XS | none | `scripts/harness-notation.sh T1` produces summary.tsv with all 53 IDs | HARNESS-NGATE-005 | M1 | complete | 100 | docs/evolution/evidence-notation/T3/results.json; HARNESS-NGATE-005 | Day 1 | yes | Checkpoints are decided from bundles, not prose. | objective checkpoints
RN-P-001 | P Proof sheet & engraving | EP-N3 Honest contract | M1 | The matplotlib PDF is named a proportional proof sheet in CLI help, docs, title page and score.py docstring; 'engrave' reserved for the LilyPond backend | T0: score.py says 'Engrave' five times; README says nothing. | mislabelled | HARNESS-NENG-003 PASS | P1 | — | — | — | yes | independent | no | maintainer | reference | — | push | none | XS | none | grep finds no 'engrave' for the proof sheet | HARNESS-NENG-003 | M1 honesty gate | complete | 100 | docs/evolution/evidence-notation/T3/results.json; HARNESS-NENG-003 | Day 1 | yes | The starting analysis is right: it is a proof sheet, not engraving. | —
RN-T-001 | T Tuning | EP-N3 Honest contract | M1 | Interim `tuning_not_rendered` diagnostic (registered code) whenever `notation.tuning` is non-12-EDO, until the resolver lands | T0: `tuning: edo divisions=19` compiles silently and renders 12-TET (AF-M05, a correctness defect by the roadmap's own words). | silent acceptance | HARNESS-NTUN-003 PASS | P0 | — | — | — | yes | independent | no | maintainer | reference | — | push | none | XS | none | compile emits the code; manifest lists it; DSL_GAP_SPEC G6 corrected | HARNESS-NTUN-003 | M1 honesty gate | complete | 100 | docs/evolution/evidence-notation/T3/results.json; HARNESS-NTUN-003 | Day 1 | yes | PURPOSE: failure should be loud and local. | —
RN-I-001 | I Import | EP-N2 Oracle-verified interchange | M2 | MusicXML import: one layer per `<part>` (named from part-name), per-part timeline | T0: bwv66.6 (4 parts) imports as one 92 s monody. | parts flattened | HARNESS-NIMP-001 PASS | P0 | RN-O-002 | hard | RN-I-002, RN-I-004, RN-I-005 | yes | dependent | yes | maintainer | reference | — | push | none | M | RN8 subset definition | layers == parts; per-part note counts match music21 | HARNESS-NIMP-001 | M2 | complete | 100 | docs/evolution/evidence-notation/T3/results.json; HARNESS-NIMP-001 |  | no | An importer that serializes an ensemble is not an importer. | chord/voice handling
RN-I-002 | I Import | EP-N2 Oracle-verified interchange | M2 | `<chord/>`, `<backup>`, `<forward>`, `<voice>` handled: simultaneous onsets, voice-aware cursor | T0: 165 distinct onsets for a homophonic chorale. | chords serialized | HARNESS-NIMP-002 PASS | P0 | RN-I-001 | hard | RN-I-004 | yes | dependent | yes | maintainer | reference | — | push | none | M | RN8 | onset set per part equals music21 offsets | HARNESS-NIMP-002 | M2 | complete | 100 | docs/evolution/evidence-notation/T3/results.json; HARNESS-NIMP-002 |  | no | Homophony is the common case in notation. | corpus round trips
RN-I-003 | I Import | EP-N2 Oracle-verified interchange | M2 | Attribute changes honoured (divisions, time, key, tempo per measure); tied notes merged into one event |  | first attributes only; ties as separate notes | HARNESS-NIMP-003 PASS | P1 | RN-I-001 | hard | RN-I-004 | yes | dependent | no | maintainer | reference | — | push | none | S | none | imported tempo_map/key_map/meter match the source | HARNESS-NIMP-003 | M2 | complete | 100 | docs/evolution/evidence-notation/T3/results.json; HARNESS-NIMP-003 |  | no | Scores change key, meter and tempo. | —
RN-X-001 | X Notated export | EP-N2 Oracle-verified interchange | M2 | Meter beats and unit from the spec (`<beat-type>` no longer hard-coded to 4), bar length derived from the spec rather than `--bars`; per-part polymeter as per-part time signatures where an engraver accepts it, else lossy code | T0: a 7/8 spec exports as 7/4. | beat-type hard-coded; bar length from a CLI flag | HARNESS-NXML-002 PASS | P0 | RN-O-002 | hard (fixtures) | RN-X-004 | yes | dependent | yes | maintainer | reference | — | push | none | S | RN11 polymeter representation | NXML-002 PASS on all fixtures; LilyPond still zero warnings | HARNESS-NXML-002 | M2 | complete | 100 | docs/evolution/evidence-notation/T3/results.json; HARNESS-NXML-002 |  | no | A wrong time signature is a wrong score. | pickup, tempo/key placement
RN-X-002 | X Notated export | EP-N2 Oracle-verified interchange | M2 | `key_map` → `<key>` at the measure of each change | T0: only the initial key is emitted (18 `<key>` = one per part). | key changes dropped silently | HARNESS-NXML-003 PASS | P1 | RN-X-001 | hard | — | yes | dependent | no | maintainer | reference | — | push | none | S | none | music21 key-signature list per part equals the spec key_map | HARNESS-NXML-003 | M2 | complete | 100 | docs/evolution/evidence-notation/T3/results.json; HARNESS-NXML-003 |  | no | Modulation is part of the authored contract. | —
RN-X-003 | X Notated export | EP-N2 Oracle-verified interchange | M2 | `tempo_map` → `<direction><metronome>` + `<sound tempo>` at each change (rubato-dense maps thinned to a documented resolution) | T0: one tempo for 43 points. | single tempo | HARNESS-NXML-004 PASS | P1 | RN-X-001 | hard | — | yes | dependent | no | maintainer | reference | — | push | none | S | none | music21 MetronomeMark count equals thinned tempo points | HARNESS-NXML-004 | M2 | complete | 100 | docs/evolution/evidence-notation/T3/results.json; HARNESS-NXML-004 |  | no | Tempo is render data; the score must not contradict the render. | —
RN-X-004 | X Notated export | EP-N2 Oracle-verified interchange | M2 | Pickup as an anacrusis measure (implicit, number 0) with downbeat-aligned measures | The exporter has no pickup handling. | pickup ignored | HARNESS-NXML-005 PASS | P1 | RN-X-001 | hard | — | yes | dependent | no | maintainer | reference | — | push | none | S | none | music21 first measure is a pickup of the declared length | HARNESS-NXML-005 | M2 | complete | 100 | docs/evolution/evidence-notation/T3/results.json; HARNESS-NXML-005 |  | no | `pickup:` is a documented score field. | —
RN-X-005 | X Notated export | EP-N2 Oracle-verified interchange | M2 | Exact-tick exporter emits one part per layer and `<chord/>` for simultaneous onsets; MIDI exporter writes one track per layer and the tempo map | T0: raw MusicXML serializes chord tones sequentially (30 vs 24 beats); MIDI export of the orchestral piece is one track with 1 315 of 2 580 notes and one tempo. | flattened, lossy | HARNESS-NXML-009, NMIDI-002, NMIDI-003 PASS | P0 | RN-O-002 | hard | RN-I-005 | yes | dependent | yes | maintainer | reference | — | push | none | M | none | music21 reads parts == layers, notes == spec notes, tempo marks == tempo points | HARNESS-NXML-009, HARNESS-NMIDI-002, HARNESS-NMIDI-003 | M2 | complete | 100 | docs/evolution/evidence-notation/T3/results.json; HARNESS-NXML-009, HARNESS-NMIDI-002, HARNESS-NMIDI-003 |  | no | INTEROP.md claims MIDI preserves pitch, start, duration and note order; it does not for polyphony across layers. | self round trip
RN-A-001 | A Analysis | EP-N3 Honest contract | M3 | Documented ambiguity set (dim7, aug, min7≡6, m7b5≡m6, sus2≡sus4) with the parity test against music21 (roots agree on all non-symmetric qualities; the 7sus4/dom7sus4 naming dispute recorded) | T0: 154 of 300 closed voicings agree with music21's root; 120 are our deliberate 'ambiguous'; 26 are two quality families where music21 names a quartal chord. | behaviour present, undocumented | HARNESS-NANA-001, NANA-002 PASS | P1 | RN-O-001 | hard | — | yes | dependent | no | maintainer | reference + oracles | — | push | none | S | none | parity test green; MIGRATION_3.md/DSL_SPEC list the ambiguous set | HARNESS-NANA-001, HARNESS-NANA-002 | M3 | complete | 100 | docs/evolution/evidence-notation/T3/results.json; HARNESS-NANA-001, HARNESS-NANA-002 |  | no | 'Evidence-based harmony' needs its evidence stated. | —
RN-D-001 | D Docs & contract | EP-N3 Honest contract | M3 | Capability manifest: `notation` directives (tuning, tuplet, lyrics) with rendering status, `interop.coverage` matrix, `score.proof_sheet` entry | T0: tuplet and lyrics absent from the manifest. | incomplete | HARNESS-NDOC-002 PASS | P1 | RN-X-010 | hard | — | yes | dependent | no | maintainer | reference | — | push | none | S | none | manifest-check green; tests/test_manifest_registry_coverage extended | HARNESS-NDOC-002 | M3 contract gate | complete | 100 | docs/evolution/evidence-notation/T3/results.json; HARNESS-NDOC-002 |  | no | G9 manifest completeness. | —
RN-I-004 | I Import | EP-N2 Oracle-verified interchange | M3 | Vendored public-domain corpus fixtures (two Bach chorales as MusicXML from music21's corpus) with round-trip tests: duration within 1 %, notes per part equal, imported spec validates and renders |  | no real-world fixtures (G8 said 'focused in-repo fixtures') | HARNESS-NIMP-004 PASS | P1 | RN-I-001, RN-I-002, RN-I-003 | hard | — | yes | dependent | no | maintainer | reference + oracles | — | push | none | S | RN3 fixture licence (public domain chorales) | NIMP-004 PASS | HARNESS-NIMP-004 | M3 | complete | 100 | docs/evolution/evidence-notation/T3/results.json; HARNESS-NIMP-004 |  | no | AI-CORE pillar: real-world fixture coverage. | —
RN-I-005 | I Import | EP-N2 Oracle-verified interchange | M3 | Self round trip: notated export → import → same parts, onsets and pitch multisets (quantization documented) |  | fails (import flattens) | HARNESS-NIMP-005 PASS | P1 | RN-X-005, RN-I-001, RN-I-002 | hard | — | yes | dependent | no | maintainer | reference | — | push | none | S | none | NIMP-005 PASS on all fixtures | HARNESS-NIMP-005 | M3 | complete | 100 | docs/evolution/evidence-notation/T3/results.json; HARNESS-NIMP-005 |  | no | Semantic round-trip preservation is an AI-CORE pillar. | —
RN-X-006 | X Notated export | EP-N2 Oracle-verified interchange | M3 | `dynamic` marks → `<dynamics>` (and hairpins as `<wedge>` where two marks bracket a span) | T0: zero `<dynamics>` in a piece with dynamic curves; lossy_dynamic_curve reported. | lossy | HARNESS-NXML-006 PASS | P2 | RN-X-001 | hard | — | yes | dependent | no | maintainer | reference | — | push | none | S | none | music21 Dynamic objects match the marks | HARNESS-NXML-006 | M3 | complete | 100 | docs/evolution/evidence-notation/T3/results.json; HARNESS-NXML-006 |  | no | Dynamics are the most common expressive notation. | —
RN-X-007 | X Notated export | EP-N2 Oracle-verified interchange | M3 | `art` → `<articulations>`, slur groups → `<slur type=start/stop>`; lossy_articulation extended to MusicXML where unrepresentable | T0: zero slurs/articulations exported; lossy_articulation only for MIDI. | dropped silently for MusicXML | HARNESS-NXML-007 PASS | P2 | RN-X-001 | hard | — | yes | dependent | no | maintainer | reference | — | push | none | S | none | music21 Articulation/Slur spanners match | HARNESS-NXML-007 | M3 | complete | 100 | docs/evolution/evidence-notation/T3/results.json; HARNESS-NXML-007 |  | no | Silent loss contradicts PURPOSE. | —
RN-X-008 | X Notated export | EP-N2 Oracle-verified interchange | M3 | `holds` → `<fermata>`; form sections → `<rehearsal>` marks; repeats already expanded (documented) |  | dropped | HARNESS-NXML-008 PASS | P2 | RN-X-001 | hard | — | yes | dependent | no | maintainer | reference | — | push | none | XS | none | fermata count == holds; rehearsal marks == sections | HARNESS-NXML-008 | M3 | complete | 100 | docs/evolution/evidence-notation/T3/results.json; HARNESS-NXML-008 |  | no | Form and holds are authored structure. | —
RN-X-009 | X Notated export | EP-N2 Oracle-verified interchange | M3 | `notation.tuplets` → `<time-modification>`; `notation.lyrics` → `<lyric>` (metadata projection only; non-vocal scope untouched) | G6 metadata exists but is not projected. | lossy_lyrics; tuplets dropped | HARNESS-NSEM-002 PASS | P3 | RN-X-001 | hard | — | yes | dependent | no | maintainer | reference | — | push | none | S | RN10 lyrics vs non-vocal scope (metadata only) | music21 reads tuplets and lyrics from the export | HARNESS-NSEM-002 | M3 | complete | 100 | docs/evolution/evidence-notation/T3/results.json; HARNESS-NSEM-002 |  | no | Metadata that never leaves the IR is not interchange. | —
RN-X-010 | X Notated export | EP-N3 Honest contract | M3 | `interop.coverage()` registry (construct × format → preserved ¦ quantized ¦ lossy code ¦ unsupported), generated INTEROP.md matrix with `--check`, lossy diagnostics derived from the same registry | T0: INTEROP.md lists four codes and one sentence of coverage; the matrix must be generator-owned like the other contracts. | hand-written prose | HARNESS-NXML-011, NSEM-001, NDOC-001 PASS | P1 | RN-X-005..009 | hard | RN-D-001 | yes | dependent | yes | maintainer | reference | — | push | none | M | none | matrix check green; every score_layer/notation construct has a row per format | HARNESS-NXML-011, HARNESS-NSEM-001, HARNESS-NDOC-001 | M3 contract gate | complete | 100 | docs/evolution/evidence-notation/T3/results.json; HARNESS-NXML-011, HARNESS-NSEM-001, HARNESS-NDOC-001 |  | no | AF-R06/R07 discipline: one source of truth and a --check twin. | manifest coverage
RN-T-002 | T Tuning | EP-N4 Tuning | M4 | `audioforge/tuning.py` n-EDO resolver threaded through note_to_freq, sampler resample ratio and plan; default path byte-identical; FFT proof test | AF-M05 slice 1 (n-EDO only). | inert | HARNESS-NTUN-001, NTUN-002 PASS | P1 | RN-T-001 | soft | RN-T-003 | yes | dependent | yes | maintainer | reference | — | push | none | M | RN4 hash change for tuning specs (none exist); RN12 sampler pitch paths | 19-EDO render places the fundamental at the specified cents ± 5 (FFT); goldens unchanged | HARNESS-NTUN-001, HARNESS-NTUN-002 | M4 migration gate | not-started | 0 | tests/test_tuning.py | ADR required (render semantics). | no | The DSL advertises microtuning it does not deliver. | microtonal interop
RN-T-003 | T Tuning | EP-N4 Tuning | M4 | Microtonal pitches export as MIDI pitch bend and MusicXML `<alter>` with decimal semitones; lossy code where unrepresentable |  | n/a | HARNESS-NTUN-004 PASS | P2 | RN-T-002, RN-X-005 | hard | — | yes | dependent | no | maintainer | reference | — | push | none | S | none | music21 reads microtonal alters; MIDI bend range documented | HARNESS-NTUN-004 | M4 | not-started | 0 | tests |  | no | A tuning that cannot leave the engine is not interchange. | —
RN-A-002 | A Analysis | EP-N5 Analysis surface | M5 | `analyze` op accepts `pitch_classes`/notes and returns normal form, prime form, interval-class vector, set class (theory_pcset) with `assessment_scope` | AF-M01 is done but unreachable for agents. | internal only | HARNESS-NANA-004 PASS | P2 | — | — | — | yes | independent | no | maintainer | reference | — | push | none | S | none | agent_tools + MCP return set-class fields; docs updated | HARNESS-NANA-004 | M5 | not-started | 0 | tests/test_mcp_contract.py | Decision D5. | no | Theory that agents cannot call does not exist for them. | —
RN-O-004 | O Oracles & gate | EP-N2 Oracle-verified interchange | M5 | CI job installing the `oracles` extra and running `make oracle-check` on Python 3.12 | Blocked by the same Actions startup failure as the release roadmap (RM-B-002). | Actions never execute | HARNESS-NORA-004 PASS | P1 | RN-O-003; external: RM-B-002 (Actions fixed) | hard, external | — | yes | dependent | no | maintainer + repo admin | GitHub Actions | Actions minutes | admin | — | S | RN6 CI dead | a green oracle job on the branch head | HARNESS-NORA-004 | M5 | blocked | 0 | gh run list |  | no | Local-only oracle runs repeat the release roadmap's original failure mode. | remote evidence
RN-P-002 | P Proof sheet & engraving | EP-N3 Honest contract | M5 | Dynamics letters drawn with a text font (Noto Music lacks Latin glyphs): zero missing-glyph warnings | T0: six warnings in the suite (glyphs 'l', 'p'). | warnings | HARNESS-NENG-004 PASS | P3 | — | — | — | yes | independent | no | maintainer | reference | — | push | none | XS | none | pytest -W error on score tests passes | HARNESS-NENG-004 | M5 | not-started | 0 | test log |  | no | Warnings that everyone ignores hide the next real one. | —
RN-P-003 | P Proof sheet & engraving | EP-N2 Oracle-verified interchange | M5 | `audioforge score --engrave`: notated export → musicxml2ly → lilypond via the `oracles`/`engrave` extra; structured message when absent | T0: LilyPond engraves our export with zero warnings in 3 s for 116 bars; the path exists, only the verb is missing. | manual only | HARNESS-NENG-002 PASS | P2 | RN-O-001, RN-X-001 | hard | — | yes | dependent | no | maintainer | reference + extra | lilypond wheel | push | none | S | RN9 wheel platform coverage | PDF produced with the extra; exit code and hint without | HARNESS-NENG-002 | M5 | not-started | 0 | CLI test | Decision D4. | no | Real engraving at zero implementation cost, honestly attributed. | —
RN-Q-001 | Q Performance | EP-N2 Oracle-verified interchange | M5 | Budget tests: notated export ≤ 1 s and MIDI export ≤ 0.5 s for 3 000 notes; import ≤ 1 s for a 4-part chorale; LilyPond ≤ 30 s for 116 bars (skips without the extra); proof sheet ≤ 15 s for 116 bars | T0: 0.05 s / 0.01 s / 0.001 s / 3.2 s / 9.8 s. | unmeasured in tests | HARNESS-NPERF-001…004 PASS | P3 | RN-O-002 | hard | — | yes | dependent | no | maintainer | reference | — | push | none | XS | none | budget tests green | HARNESS-NPERF-001, HARNESS-NPERF-002, HARNESS-NPERF-003, HARNESS-NPERF-004 | M5 performance gate | not-started | 0 | tests/test_notation_perf.py |  | no | Budgets stop regressions from being discovered by users. | —
RN-A-003 | A Analysis | EP-N5 Analysis surface | decision | Decision D3: in-process music21 bridge (`analyze --musicology`) or export-only delegation | Recommended: export-only; music21 results are external and must be labelled as such. | no bridge | ADR-0011 records the decision | P3 | RN-D-004 | hard | — | yes | dependent | no | maintainer | — | — | — | — | XS | none | decision recorded | HARNESS-NANA-005 | M1 | complete | 100 | docs/evolution/evidence-notation/T3/results.json; HARNESS-NANA-005 |  | no | Avoid re-implementing musicology the ecosystem already has. | —
RN-T-004 | T Tuning | EP-N4 Tuning | post-M6 (AF-M05 remainder) | Just intonation tables, historical temperaments (Barbour cents), Scala .scl/.kbm import | Out of this plan's T6; tracked as AF-M05 in the backlog. | not started | — | P3 | RN-T-002 | hard | — | yes | dependent | no | unassigned | reference | — | push | none | L | RN7 scope creep | AF-M05 DoD | — | — | parked | 0 | docs/backlog.yml BL-022 | Deliberately excluded from T6. | no | Recorded so the boundary of this plan is explicit. | —

## Dependencies
Depends on (from) | Item (to) | Type | Why the dependency exists | From (short) | To (short)
RN-O-001 | RN-O-003 | hard | Oracle tests cannot run without the oracles. | `oracles` dev extra (music21, lilypond wheel, xmlschema) + v | tests/test_notation_oracles.py: XSD validity, music21 parity
RN-O-002 | RN-O-003 | hard | Parity needs a versioned fixture corpus. | Fixture corpus tests/fixtures/notation/*.af (≥ 8 specs) with | tests/test_notation_oracles.py: XSD validity, music21 parity
RN-O-003 | RN-O-004 | hard | CI can only run tests that exist. | tests/test_notation_oracles.py: XSD validity, music21 parity | CI job installing the `oracles` extra and running `make orac
RN-O-001 | RN-O-005 | soft | The runner calls the oracles for most rows. | `oracles` dev extra (music21, lilypond wheel, xmlschema) + v | `scripts/harness-notation.sh` (from harness-notation.md §8)
RN-O-002 | RN-X-001 | hard | Exporter changes are judged on the corpus. | Fixture corpus tests/fixtures/notation/*.af (≥ 8 specs) with | Meter beats and unit from the spec (`<beat-type>` no longer
RN-X-001 | RN-X-002 | hard | Key placement needs correct measures. | Meter beats and unit from the spec (`<beat-type>` no longer | `key_map` → `<key>` at the measure of each change
RN-X-001 | RN-X-003 | hard | Tempo placement needs correct measures. | Meter beats and unit from the spec (`<beat-type>` no longer | `tempo_map` → `<direction><metronome>` + `<sound tempo>` at
RN-X-001 | RN-X-004 | hard | A pickup is a measure-structure change. | Meter beats and unit from the spec (`<beat-type>` no longer | Pickup as an anacrusis measure (implicit, number 0) with dow
RN-O-002 | RN-X-005 | hard | Chord/part fidelity is judged on the corpus. | Fixture corpus tests/fixtures/notation/*.af (≥ 8 specs) with | Exact-tick exporter emits one part per layer and `<chord/>`
RN-X-001 | RN-X-006 | hard | Dynamics attach to measures. | Meter beats and unit from the spec (`<beat-type>` no longer | `dynamic` marks → `<dynamics>` (and hairpins as `<wedge>` wh
RN-X-001 | RN-X-007 | hard | Slurs attach to measured notes. | Meter beats and unit from the spec (`<beat-type>` no longer | `art` → `<articulations>`, slur groups → `<slur type=start/s
RN-X-001 | RN-X-008 | hard | Fermatas and rehearsal marks attach to measures. | Meter beats and unit from the spec (`<beat-type>` no longer | `holds` → `<fermata>`; form sections → `<rehearsal>` marks;
RN-X-001 | RN-X-009 | hard | Tuplets are measure-relative. | Meter beats and unit from the spec (`<beat-type>` no longer | `notation.tuplets` → `<time-modification>`; `notation.lyrics
RN-X-005 | RN-X-010 | hard | The matrix records what the exporters actually do. | Exact-tick exporter emits one part per layer and `<chord/>` | `interop.coverage()` registry (construct × format → preserve
RN-X-009 | RN-X-010 | hard | The matrix records the last projected constructs. | `notation.tuplets` → `<time-modification>`; `notation.lyrics | `interop.coverage()` registry (construct × format → preserve
RN-X-010 | RN-D-001 | hard | Manifest coverage is derived from the registry. | `interop.coverage()` registry (construct × format → preserve | Capability manifest: `notation` directives (tuning, tuplet,
RN-O-002 | RN-I-001 | hard | Import fidelity is judged on the corpus. | Fixture corpus tests/fixtures/notation/*.af (≥ 8 specs) with | MusicXML import: one layer per `<part>` (named from part-nam
RN-I-001 | RN-I-002 | hard | Chords are per part. | MusicXML import: one layer per `<part>` (named from part-nam | `<chord/>`, `<backup>`, `<forward>`, `<voice>` handled: simu
RN-I-001 | RN-I-003 | hard | Attribute changes are per part. | MusicXML import: one layer per `<part>` (named from part-nam | Attribute changes honoured (divisions, time, key, tempo per
RN-I-001 | RN-I-004 | hard | Corpus round trip needs parts. | MusicXML import: one layer per `<part>` (named from part-nam | Vendored public-domain corpus fixtures (two Bach chorales as
RN-I-002 | RN-I-004 | hard | Corpus round trip needs chords. | `<chord/>`, `<backup>`, `<forward>`, `<voice>` handled: simu | Vendored public-domain corpus fixtures (two Bach chorales as
RN-I-003 | RN-I-004 | hard | Corpus round trip needs attribute changes. | Attribute changes honoured (divisions, time, key, tempo per | Vendored public-domain corpus fixtures (two Bach chorales as
RN-X-005 | RN-I-005 | hard | Self round trip needs the multi-part exporter. | Exact-tick exporter emits one part per layer and `<chord/>` | Self round trip: notated export → import → same parts, onset
RN-I-002 | RN-I-005 | hard | Self round trip needs chord import. | `<chord/>`, `<backup>`, `<forward>`, `<voice>` handled: simu | Self round trip: notated export → import → same parts, onset
RN-T-001 | RN-T-002 | soft | The interim diagnostic is removed when the resolver lands. | Interim `tuning_not_rendered` diagnostic (registered code) w | `audioforge/tuning.py` n-EDO resolver threaded through note_
RN-T-002 | RN-T-003 | hard | Nothing to export before microtones render. | `audioforge/tuning.py` n-EDO resolver threaded through note_ | Microtonal pitches export as MIDI pitch bend and MusicXML `<
RN-X-005 | RN-T-003 | hard | Per-part exporters carry the microtonal alters. | Exact-tick exporter emits one part per layer and `<chord/>` | Microtonal pitches export as MIDI pitch bend and MusicXML `<
RN-T-002 | RN-T-004 | hard | JI and temperaments extend the resolver. | `audioforge/tuning.py` n-EDO resolver threaded through note_ | Just intonation tables, historical temperaments (Barbour cen
RN-O-001 | RN-A-001 | hard | Parity is measured against music21. | `oracles` dev extra (music21, lilypond wheel, xmlschema) + v | Documented ambiguity set (dim7, aug, min7≡6, m7b5≡m6, sus2≡s
RN-D-004 | RN-A-003 | hard | The bridge decision lives in the positioning ADR. | ADR-0011: notation positioning — semantic score contract + o | Decision D3: in-process music21 bridge (`analyze --musicolog
RN-O-001 | RN-P-003 | hard | The engraving backend uses the wheel. | `oracles` dev extra (music21, lilypond wheel, xmlschema) + v | `audioforge score --engrave`: notated export → musicxml2ly →
RN-X-001 | RN-P-003 | hard | Engraving a wrong time signature is worse than none. | Meter beats and unit from the spec (`<beat-type>` no longer | `audioforge score --engrave`: notated export → musicxml2ly →
RN-D-004 | RN-D-002 | soft | README states the decided positioning. | ADR-0011: notation positioning — semantic score contract + o | README section 'Notation and analysis': semantic score field
RN-O-002 | RN-Q-001 | hard | Budgets are measured on fixtures. | Fixture corpus tests/fixtures/notation/*.af (≥ 8 specs) with | Budget tests: notated export ≤ 1 s and MIDI export ≤ 0.5 s f
RM-B-002 (release roadmap) | RN-O-004 | external | GitHub Actions must execute jobs. | RM-B-002 (release roadmap) | CI job installing the `oracles` extra and running `make orac

## Milestones
Milestone | Checkpoint | Name | Objective | Entry criteria | Exit gate (harness rows that must be PASS) | Unlocks | Status
M0 | T0 | Baseline | Measure the notation, interop and analysis surface against external oracles | — | 53 assertions executed; §4 of harness-notation.md | M1 | complete (2026-09-06)
M1 | T1 | Honesty and oracles | Say what the surface is, and make the oracles part of the toolchain: `oracles` dev extra, vendored XSD, fixture corpus, runner, ADR-0011, proof-sheet labelling, interim tuning diagnostic | M0 | HARNESS-NORA-001/002/003, NGATE-001, NENG-003, NTUN-003, NDOC-005 PASS | M2 | complete (T3 evidence)
M2 | T2 | Interchange core | Notated export derives structure from the spec (meter unit, bar length, key and tempo changes, pickup); chords and parts in both exporters; multi-part, chord-aware import | M1 | HARNESS-NXML-002…005, NXML-009, NIMP-001…003, NMIDI-002/003 PASS | M3 | complete (T3 evidence)
M3 | T3 | Oracle integration | music21 and LilyPond parity green on the fixture corpus; expressive notation projected; generated coverage matrix and manifest entries | M2 | HARNESS-NXML-001, NXML-006…008, NXML-010/011, NIMP-004/005, NSEM-001/002, NDOC-001/002, NANA-001/002 PASS | M4 | complete (T3 evidence)
M4 | T4 | Tuning activation | The `tuning:` directive drives the render (n-EDO slice) with FFT proof; default path byte-identical; microtonal interop documented | M3 | HARNESS-NTUN-001/002/004 PASS; goldens unchanged | M5 | not-started
M5 | T5 | Hardening | Perf budgets, glyph fix, optional LilyPond engraving backend, corpus round trips, CI oracle job when Actions execute | M4 | HARNESS-NPERF-001…004, NENG-002/004, NANA-004, NORA-004 PASS or waived | M6 | not-started
M6 | T6 | Desired state | Engine 3.1.0 / DSL 2.1: notation surface honest, interchange oracle-verified, tuning real; all non-waived rows PASS | M5 | every HARNESS-N row PASS except live waivers; README/INTEROP/manifest agree; release gate | — | not-started

## Harness Coverage
Harness ID | Category | Requirement (short) | Mode | T0 result | T0 detail | Target | Roadmap items | Green by
HARNESS-NORA-001 | NORA | The `oracles` dev extra installs music21, the LilyPond wheel and xmlschema | A | FAIL | FAIL: no such extra (T0 oracles live in a scratch venv) | PASS | RN-O-001 | T1
HARNESS-NORA-002 | NORA | The MusicXML 3.1 XSD is vendored with its licence and used offline | A | FAIL | FAIL: fetched to scratch at T0 (335 762 + 5 695 + 2 280 bytes), not in tree | PASS | RN-O-001 | T1
HARNESS-NORA-003 | NORA | `make oracle-check` runs the oracle tests and skips loudly without the extra | A | FAIL | FAIL: no target, no oracle tests | PASS | RN-O-003 | T1 (skeleton), T3 (green)
HARNESS-NORA-004 | NORA | A CI job installs the extra and runs `make oracle-check` | A | BLOCKED | BLOCKED: GitHub Actions end in `startup_failure` for every run (release harness HARNESS-CI-001) | PASS | RN-O-004 | T5
HARNESS-NXML-001 | NXML | (oracle) Every fixture's notated export validates against the MusicXML 3.1 XSD | A | PARTIAL | PARTIAL: VALID on the two ad-hoc specs and on the 116-bar piece; no committed corpus yet | PASS | RN-O-003 | T3
HARNESS-NXML-002 | NXML | Meter beats and unit come from the spec; bar length from the spec, not a CLI flag; per-part polymeter as per-part time signatures or a lossy code | A | FAIL | FAIL: exports `7/4` (`beat-type` hard-coded to 4; `beats_per_bar` from `--bars`) | PASS | RN-X-001 | T2
HARNESS-NXML-003 | NXML | `key_map` changes appear as `<key>` at the measure of change | A | FAIL | FAIL: one `<key>` per part, initial key only | PASS | RN-X-002 | T2
HARNESS-NXML-004 | NXML | `tempo_map` changes appear as `<direction>`/`<sound tempo>` at their measures (dense rubato maps thinned to a documented resolution) | A | FAIL | FAIL: exactly one `<sound tempo>` | PASS | RN-X-003 | T2
HARNESS-NXML-005 | NXML | `pickup:` exports as an anacrusis (implicit measure) and downbeats align | A | FAIL | FAIL: no pickup handling in `interop.py` | PASS | RN-X-004 | T2
HARNESS-NXML-006 | NXML | `dynamic` marks export as `<dynamics>` | A | FAIL | FAIL: 0 `<dynamics>` in a piece with dynamic curves (lossy_dynamic_curve reported) | PASS | RN-X-006 | T3
HARNESS-NXML-007 | NXML | `art` and slur groups export as `<articulations>` and `<slur>`; unrepresentable ones carry `lossy_articulation` for MusicXML too | A | FAIL | FAIL: 0 emitted; `lossy_articulation` is reported for MIDI only | PASS | RN-X-007 | T3
HARNESS-NXML-008 | NXML | `holds` export as `<fermata>`; form sections as `<rehearsal>` marks | A | FAIL | FAIL: neither emitted | PASS | RN-X-008 | T3
HARNESS-NXML-009 | NXML | The exact-tick exporter (`export_musicxml`) emits one part per layer and `<chord/>` for simultaneous onsets | A | FAIL | FAIL: 1 part, 0 `<chord/>`; chord tones serialized (music21 reads 30 beats of note time for 24) | PASS | RN-X-005 | T2
HARNESS-NXML-010 | NXML | (oracle) music21 structural parity per fixture: parts = pitched layers, measures = ceil(duration / bar), time signatures = meter(s), key signatures = key_map, pitch multiset per pa | A | PARTIAL | PARTIAL: parts, measures and pitch multisets match on the fixture (2 parts, 4 measures, 3/4, fifths 1); meter unit and key changes fail (NXML-002/003) | PASS | RN-O-003 | T3
HARNESS-NXML-011 | NXML | Lossy diagnostics enumerate exactly the constructs each export dropped, and the INTEROP.md matrix is generated from the same registry | A | FAIL | FAIL: four hand-listed codes; no matrix; pickup/tempo/key/holds dropped silently | PASS | RN-X-010 | T3
HARNESS-NIMP-001 | NIMP | One layer per `<part>`, named from `part-name` | A | FAIL | FAIL: 1 layer for 4 parts | PASS | RN-I-001 | T2
HARNESS-NIMP-002 | NIMP | `<chord/>`, `<backup>`, `<forward>`, `<voice>` produce simultaneous onsets and voice-aware cursors | A | FAIL | FAIL: 165 distinct onsets for 165 notes; 144 beats laid end to end | PASS | RN-I-002 | T2
HARNESS-NIMP-003 | NIMP | `divisions`, `<time>`, `<key>`, `<sound tempo>` changes are honoured per measure; ties merge into one event | A | FAIL | FAIL: the importer reads the first `divisions` and first `sound` only; ties stay separate | PASS | RN-I-003 | T2
HARNESS-NIMP-004 | NIMP | (oracle) Corpus round trip: music21 corpus piece → our import: duration within 1 %, notes per part equal, spec validates and renders | A | FAIL | FAIL: 91.875 s for a 25 s chorale; single part | PASS | RN-I-004 | T3
HARNESS-NIMP-005 | NIMP | Self round trip: notated export → import → same parts, onsets and pitch multisets (quantization documented) | A | FAIL | FAIL (import flattens parts) | PASS | RN-I-005 | T3
HARNESS-NMIDI-001 | NMIDI | Multi-track MIDI import keeps parts and timing | A | PASS | PASS: 4 layers (36/42/44/41 notes), 22.5 s, 96 bpm | PASS | RN-O-003 | T1
HARNESS-NMIDI-002 | NMIDI | (oracle) MIDI export writes one track per layer and every note survives | A | FAIL | FAIL: 1 part, 1 315 notes (single channel; same-pitch notes across layers cut each other) | PASS | RN-X-005 | T2
HARNESS-NMIDI-003 | NMIDI | MIDI export carries the tempo map as tempo events | A | FAIL | FAIL: 1 tempo event (`bpm` only; `tempo_map` ignored) | PASS | RN-X-005 | T2
HARNESS-NTUN-001 | NTUN | `tuning: edo divisions=19` drives the render | A | FAIL | FAIL: renderer never reads `notation.tuning`; B4 renders at 493.883 Hz (12-TET) | PASS | RN-T-002 | T4
HARNESS-NTUN-002 | NTUN | Without a tuning directive, renders are byte-identical to today | A | PASS | PASS: goldens byte-for-byte on `16b2cc2` | PASS | RN-T-002 | T4
HARNESS-NTUN-003 | NTUN | Until NTUN-001 passes, a non-12-EDO tuning compiles with a registered `tuning_not_rendered` diagnostic (the row becomes N/A once NTUN-001 passes) | A | FAIL | FAIL: compiles with no diagnostic | PASS | RN-T-001 | T1
HARNESS-NTUN-004 | NTUN | Microtonal pitches export as MIDI pitch bend and MusicXML decimal `<alter>`; unrepresentable cases carry a code | A | FAIL | FAIL (nothing microtonal exists to export) | PASS | RN-T-003 | T4
HARNESS-NANA-001 | NANA | (oracle) Chord roots agree with music21 for non-symmetric qualities | A | PASS | PASS: 154 of 156 (98.7 %); disputes recorded: `7sus4`/`dom7sus4` (music21 names the quartal tetramirror from the fourth), two `dim` spellings | PASS | RN-A-001, RN-O-003 | T3
HARNESS-NANA-002 | NANA | Symmetric and relative collections are declared ambiguous with candidates, and the documented set matches exactly | A | PARTIAL | PARTIAL: behaviour present (120 ambiguous, 0 unrecognized); docs mention only C6/Am7 | PASS | RN-A-001 | T3
HARNESS-NANA-003 | NANA | Analysis reports state their scope; no key-finding, roman-numeral or realism claim is made | A | PASS | PASS: `signal_and_declared_expectations; musical merit requires listening`; voicing documented as a bounded transformation | PASS | RN-O-003 | T1
HARNESS-NANA-004 | NANA | Pitch-class-set theory (AF-M01) is reachable through `analyze` (normal form, prime form, IC vector, set class) | A | FAIL | FAIL: `theory_pcset` is internal only | PASS | RN-A-002 | T5
HARNESS-NANA-005 | NANA | The music21-bridge decision (D3) is recorded | A | FAIL | FAIL | PASS | RN-A-003 | T1
HARNESS-NENG-001 | NENG | (oracle) Every fixture's notated export engraves through `musicxml2ly` + `lilypond` with zero warnings | A | PASS | PASS: fixture and 116-bar piece, 0 warnings, 3.2 s | PASS | RN-O-003 | T3
HARNESS-NENG-002 | NENG | `audioforge score --engrave` uses the LilyPond backend when the extra is installed and gives a structured hint otherwise | A | FAIL | FAIL: no such option | PASS | RN-P-003 | T5
HARNESS-NENG-003 | NENG | The matplotlib PDF is named a proportional proof sheet everywhere; the word "engrave" is reserved for LilyPond | A | FAIL | FAIL: `score.py` says "Engrave" five times | PASS | RN-P-001 | T1
HARNESS-NENG-004 | NENG | The proof sheet renders dynamics text without missing-glyph warnings | A | FAIL | FAIL: six `Glyph … missing from font(s) Noto Music` warnings (letters `l`, `p`) | PASS | RN-P-002 | T5
HARNESS-NDOC-001 | NDOC | `docs/INTEROP.md` carries a generated coverage matrix (construct × format → preserved / quantized / lossy code / unsupported) with a `--check` twin | A | FAIL | FAIL: prose with four codes | PASS | RN-X-010 | T3
HARNESS-NDOC-002 | NDOC | The capability manifest lists notation directives (`tuning`, `tuplet`, `lyrics`) with rendering status and the interop coverage | A | FAIL | FAIL: `tuplet` and `lyrics` absent; `score_layer` covers five properties only | PASS | RN-D-001 | T3
HARNESS-NDOC-003 | NDOC | README has a "Notation and analysis" section stating scope and delegation | A | FAIL | FAIL: README never mentions score, notation or MusicXML | PASS | RN-D-002 | T1
HARNESS-NDOC-004 | NDOC | `DSL_GAP_SPEC.md` G6/G8 state the measured limits (inert tuning, flattened import) with harness IDs instead of "closed" | A | FAIL | FAIL: both say closed | PASS | RN-D-003 | T1
HARNESS-NDOC-005 | NDOC | ADR-0011 records the positioning: semantic score contract, oracle-verified interchange, engraving and musicology delegated, proof sheet retained | A | FAIL | FAIL | PASS | RN-D-004 | T1
HARNESS-NGATE-001 | NGATE | A committed fixture corpus with expected-features JSON exists (≥ 8 specs) | A | FAIL | FAIL: none | PASS | RN-O-002 | T1
HARNESS-NGATE-002 | NGATE | The surface's existing tests keep passing | A | PASS | PASS: 46 passed | PASS | RN-O-003 | every checkpoint
HARNESS-NGATE-003 | NGATE | `make check` green and coverage ≥ 90.1 % with the new code | A | PASS | PASS: 910 passed on `16b2cc2`; coverage 90.96 % at 3.0.0 | PASS | RN-O-003 | every checkpoint
HARNESS-NGATE-004 | NGATE | Goldens unchanged by notation work | A | PASS | PASS | PASS | RN-O-003 | every checkpoint
HARNESS-NGATE-005 | NGATE | The runner exists and evidence bundles are tracked | A | FAIL | FAIL: runner only in §8; T0 evidence transcribed in §4.3 | PASS | RN-O-005 | T1
HARNESS-NGATE-006 | NGATE | The plan is registered in `docs/backlog.yml` | A | FAIL | FAIL | PASS | RN-D-005 | T1
HARNESS-NPERF-001 | NPERF | Notated MusicXML export ≤ 1 s and MIDI export ≤ 0.5 s for a 3 000-note spec | A | PASS | PASS: 0.05 s / 0.01 s | PASS | RN-Q-001 | T5
HARNESS-NPERF-002 | NPERF | (oracle) `musicxml2ly` + `lilypond` ≤ 30 s for 116 measures | A | PASS | PASS: 0.9 s + 3.2 s | PASS | RN-Q-001 | T5
HARNESS-NPERF-003 | NPERF | Proof-sheet PDF ≤ 15 s for 116 measures | A | PASS | PASS: 9.8 s (642 KB) | PASS | RN-Q-001 | T5
HARNESS-NPERF-004 | NPERF | MusicXML import ≤ 1 s for a four-part ten-measure chorale | A | PASS | PASS: 0.001 s (before the part-aware rewrite; re-measured at T2) | PASS | RN-Q-001 | T5
HARNESS-NSEM-001 | NSEM | Every `score_layer` property (meter, pickup, form, repeat, polymeter) has a defined projection or a registered lossy code in both exporters | A | FAIL | FAIL: meter partially (unit wrong), pickup/form/polymeter dropped silently; repeat expanded (documented) | PASS | RN-X-010 | T3
HARNESS-NSEM-002 | NSEM | `notation.tuplets` and `notation.lyrics` project to `<time-modification>` and `<lyric>`, or carry a code | A | PARTIAL | PARTIAL: `lossy_lyrics` is reported; tuplets dropped silently | PASS | RN-X-009 | T3

## Risks
ID | Category | Risk | Likelihood | Impact | Mitigation / owner item | Harness signal | Status
RN1 | operational | Oracle dependency weight (lilypond wheel plus music21) slows dev installs | medium | low | dev extra only; never a runtime dependency; skip loudly when absent | HARNESS-NORA-001 | open
RN2 | legal | Vendoring the MusicXML 3.1 XSD | low | low | W3C Community Final Specification Agreement permits redistribution with notice; include LICENSE alongside | HARNESS-NORA-002 | open
RN3 | legal | Corpus fixtures (Bach chorales) licensing | low | low | public-domain works; record provenance in the fixture README | HARNESS-NIMP-004 | open
RN4 | migration | Activating tuning changes hashes for specs with a tuning directive | low | medium | none in the repository; default path proven byte-identical by goldens (NTUN-002); MIGRATION note | HARNESS-NTUN-002 | open
RN5 | implementation | Oracle version drift (music21 heuristics, LilyPond warnings) reddens parity tests | medium | medium | pin versions in the extra; parity assertions target structural facts, not heuristics | HARNESS-NANA-001, HARNESS-NENG-001 | open
RN6 | operational | CI still fails at startup (release roadmap RM-B-002) | high | medium | oracle job waits; local oracle-check meanwhile | HARNESS-NORA-004 | open
RN7 | scope | Track M musicology (M02–M07) gets pulled into this plan | medium | medium | explicit boundary: interchange and honesty only; RN-T-004 parked | — | open
RN8 | architecture | MusicXML import subset ambiguity (voices, cross-staff, grace notes, transposing instruments) | high | medium | define the supported subset in the coverage matrix; unsupported constructs emit lossy codes, never silence | HARNESS-NXML-011, HARNESS-NIMP-002 | open
RN9 | infrastructure | LilyPond wheel availability per platform | low | low | Linux/macOS/Windows wheels exist; the verb degrades to a structured hint | HARNESS-NENG-002 | open
RN10 | scope | Lyrics export touches the non-vocal scope | low | low | metadata projection only; no vocal rendering (ADR-0002) | HARNESS-NSEM-002 | open
RN11 | architecture | Per-part polymeter has no universally accepted MusicXML rendering | medium | low | export per-part time signatures where LilyPond accepts them; lossy code otherwise | HARNESS-NXML-002 | open
RN12 | implementation | Tuning resolver must thread through sampler resample ratios and plan without changing 12-TET bytes | medium | medium | resolver returns the exact current expression when tuning is absent; goldens gate | HARNESS-NTUN-002 | open
RN13 | architecture | Quantized notated export is lossy by construction and could be mistaken for the IR | certain | low | label the projection; the exact-tick exporter remains the interchange of record | HARNESS-NXML-011 | accepted

## Resources
Kind | Resource | Needed by | Requirement | Availability at T0
Role | Maintainer | all RN items | write + push | present
Role | Repository admin | RN-O-004 | GitHub Actions/billing | pending (release roadmap)
Environment | Reference machine | all | Python 3.13 venv; Noto Music font present | present
Environment | Oracle venv | RN-O-*, RN-A-001, RN-P-003 | music21 10.5.0, lilypond 2.25.12 wheel, xmlschema 4.3.2 | present in scratch; becomes the `oracles` extra
Infrastructure | MusicXML 3.1 XSD | RN-O-001 | 3 files (~340 KB) from w3c/musicxml v3.1 | fetched at T0; to be vendored
Infrastructure | GitHub Actions | RN-O-004 | oracle job | BLOCKED: startup_failure
Permission | Push / merge | RN-* | repo write | present
Credential | API keys | — | none required | n/a
External service | PyPI (music21, lilypond, xmlschema) | RN-O-001 | network once | present

## Traceability
Requirement ID | Report requirement (report-notation.md §3) | Roadmap items | Harness tests | Evidence | Milestone exit gate
NREQ-1 | Notated MusicXML export derives structure from the spec and is oracle-valid | RN-X-001…004, RN-O-003 | HARNESS-NXML-001…005, NXML-010 | fixture exports; XSD report; music21 parity; LilyPond log | M2/M3
NREQ-2 | Exact-tick and MIDI exports preserve parts, chords and tempo | RN-X-005 | HARNESS-NXML-009, NMIDI-001…003 | music21 parse of exports | M2
NREQ-3 | Expressive and structural notation projected or declared lossy | RN-X-006…010 | HARNESS-NXML-006…008, NXML-011, NSEM-001/002 | fixture exports; generated matrix | M3
NREQ-4 | MusicXML import preserves parts, chords and attribute changes; corpus round trips | RN-I-001…005 | HARNESS-NIMP-001…005 | import tests; vendored corpus | M2/M3
NREQ-5 | The tuning directive is honest, then real | RN-T-001…003 | HARNESS-NTUN-001…004 | diagnostic; FFT proof; goldens | M1/M4
NREQ-6 | Analysis claims are stated and parity-checked | RN-A-001…003 | HARNESS-NANA-001…005 | parity test; ADR-0011 | M3/M5
NREQ-7 | The PDF is a labelled proof sheet; real engraving is delegated | RN-P-001…003 | HARNESS-NENG-001…004 | docs; LilyPond backend test | M1/M5
NREQ-8 | Contract and docs describe the surface exactly | RN-D-001…005, RN-X-010 | HARNESS-NDOC-001…005, NGATE-006 | manifest; INTEROP.md; README; ADR; backlog | M1/M3
NREQ-9 | Oracles are part of the toolchain and the gate | RN-O-001…005 | HARNESS-NORA-001…004, NGATE-001…005 | pyproject; make target; runner; CI job | M1/M5
NREQ-10 | Budgets hold | RN-Q-001 | HARNESS-NPERF-001…004 | budget tests | M5

## Decisions
ID | Decision | Recommended option | Alternative(s) | Roadmap item | Where it is decided
D1 | Tuning directive: implement the n-EDO slice, or remove the directive? | Implement n-EDO (RN-T-002) after an interim loud diagnostic (RN-T-001); default path byte-identical | Remove the directive from DSL 2.x (honest, loses the roadmap's P1 capability) | RN-T-001, RN-T-002 | M1/M4
D2 | Release vehicle | Engine 3.1.0 / DSL 2.1 after 3.0.0 ships (additive syntax; tuning activation documented as a semantic change) | Fold into 3.0.0 (delays the release; mixes concerns) | all | M6
D3 | music21 in-process bridge | No bridge: export MusicXML, let music21 analyse; document the workflow | Optional `analyze --musicology` calling music21 when installed (results labelled external) | RN-A-003 | M1
D4 | Engraving | Optional LilyPond backend via the wheel (`score --engrave`); proof sheet stays the default | Keep only the proof sheet; or add a notation engine in-house (rejected: music21/LilyPond are far ahead, as the starting analysis says) | RN-P-003 | M5
D5 | Expose pitch-class-set theory through `analyze` | Yes (S effort; AF-M01 is done and unreachable) | Leave internal | RN-A-002 | M5
D6 | Exact-tick exporter semantics | Fix: one part per layer, `<chord/>` for simultaneity, tempo map | Deprecate in favour of the notated export (loses the exact interchange) | RN-X-005 | M2
D7 | Oracle gate placement | Separate `make oracle-check` (skips loudly without the extra); CI installs the extra when Actions work | Inside `make check` (breaks local gate for anyone without the extra) | RN-O-003 | M1