## README
AudioForge — Engine 3.0 musical-correctness release roadmap
Generated by Claude Fable 5.1 via Claude Code on 2026-09-05. Disclaimer: no information in this workbook should be taken for granted; any statement not backed by a verifiable reference may be invalid, erroneous, or a hallucination. Every status here derives from docs/evolution/harness.md §4 (T0) and must be advanced only from evidence bundles.
Companion files | docs/evolution/report.md (analysis) · docs/evolution/harness.md (verification contract, T0 baseline, runner)
Baseline | T0 = 2026-09-05, working tree on main@60c0fd5 (+45 modified, +12 untracked), engine 3.0.0 / DSL 2.0 / IR 2.0 uncommitted
ID conventions | RM-<ws>-<nnn> roadmap items (ws: A verification, B portability/CI, C integration/release, D governance, E contract, F ledger rows) · HARNESS-<cat>-<nnn> assertions · M0…M6 milestones = checkpoints T0…T6 · A1–A4, M1–M6, G1 = ledger rows in docs/MUSICAL_CORRECTNESS.md
Status vocabulary | not-started · implemented (40 %) · locally-verified (60 %) · independently-reproduced (70 %) · ci-verified (90 %) · released (100 %) · complete (non-code items: acceptance criteria met and harness rows PASS in an evidence bundle)
Completion rule | An item is complete only when: implementation exists; its harness tests execute; acceptance criteria pass; the named evidence exists; the milestone exit gate accepts it. 'Done because code was written' is not a state.
Effort scale | XS / S / M / L / XL (complexity, never time)
Critical path | RM-C-001 → RM-B-001 → RM-B-002 → (HARNESS-CI-002) → RM-C-003 → RM-C-005 → RM-C-006. Everything in workstreams A, D, E runs in parallel on the branch and is pulled onto the path only through the M2/M3 gates.
Day 1 | RM-C-001, RM-B-001, RM-B-002, RM-A-001, RM-A-002, RM-C-002, RM-D-002, RM-D-003, RM-D-004, RM-D-005, RM-E-001, RM-E-003, RM-E-004 (see column 'Day 1' in Detailed Backlog)
Sheets | Executive Roadmap · Detailed Backlog · Dependencies · Milestones · Harness Coverage · Risks · Resources · Traceability
Out of scope | Track M (music theory), Track X (stochastic composition), AF-R08 Phase B (typed IR model), AF-R16 (cross-platform determinism): tracked in docs/backlog.yml, not here.

## Executive Roadmap
Milestone | Checkpoint | Name | Objective | Roadmap items | Critical-path items | Exit gate (harness) | Unlocks | Status
M0 | T0 | Current-state baseline | Measure the working tree with the harness before any change | — | — | All 59 assertions executed and recorded (harness.md §4) | M1 | complete (2026-09-05)
M1 | T1 | Foundation | Make the repair safe and the toolchain honest: commit + push, lockfile, Python 3.10, harness runner, CI root cause | RM-C-001, RM-C-002, RM-B-001, RM-B-002, RM-A-001, RM-A-002 | RM-C-001, RM-B-001, RM-B-002 | HARNESS-VCS-001, VCS-002, REL-004, PORT-001, OBS-002, GATE-006, SEC-002 = PASS; CI-001 diagnosed with owner | M2 | complete: evidence/T1 (7 PASS; CI-001 FAIL diagnosed, operator)
M2 | T2 | Core capabilities on a commit | Re-prove every functional assertion against a commit SHA, and land the small contract and record fixes | RM-B-003, RM-A-004, RM-D-004, RM-D-005, RM-D-006, RM-E-001, RM-E-003, RM-E-004, RM-F-001, RM-F-002, RM-F-003, RM-F-004, RM-F-005, RM-F-006, RM-F-007, RM-F-008, RM-F-009, RM-F-010, RM-F-011 | — | AUD-*, MUS-*, ACC-001/002/004, GATE-001…005, PORT-002…004, MIG-*, RB-001, OBS-001, PERF-001, CON-001, CON-003, CON-004, GOV-004…007 = PASS on the branch head | M3 | complete: evidence/T2 (49+1 PASS on 4157c74; 7 operator-gated FAIL; 2 MANUAL)
M3 | T3 | Integration | First remote CI execution ever; independent review; registry and ledger know the work; structured diagnostics decision recorded | RM-C-003, RM-B-002, RM-B-004, RM-D-001, RM-D-002, RM-D-003, RM-E-002 | RM-C-003, RM-B-002 | CI-001, CI-002, CI-004, VCS-003, GOV-001…003, GOV-008, CON-002 (or ADR-0008 deferral + waiver) = PASS | M4 | in-progress: GOV-001…003, CON-002 PASS on the branch; CI-001/002/004 blocked on the Actions startup failure (operator); VCS-003 awaits an approving review (operator)
M4 | T4 | Migration (merge and consolidate) | Merge to main with CI green; one coherent 3.0.0 changelog; ADR-0007 may now say implemented | RM-C-004, RM-C-005, RM-D-004, RM-F-001, RM-F-002, RM-F-003, RM-F-004, RM-F-005, RM-F-006, RM-F-007, RM-F-008, RM-F-009, RM-F-010, RM-F-011 | RM-C-005 | VCS-004, CI-003, REL-002 = PASS; GATE-001…005 re-run on main | M5 | blocked (M3 gate)
M5 | T5 | Hardening | Human listening evidence, documented resampler cost, rollback rehearsed, offline run | RM-A-003, RM-A-005, RM-E-005 | — | ACC-003 (or waiver), PERF-002, RB-002, SEC-001 = PASS | M6 | blocked (M4 gate); PERF-002, RB-002, SEC-001 already PASS on the branch; ACC-003 needs a listener
M6 | T6 | Desired state | Tags pushed; every non-waived assertion green; final evidence bundle committed; ledger reads released | RM-C-006, RM-F-001, RM-F-002, RM-F-003, RM-F-004, RM-F-005, RM-F-006, RM-F-007, RM-F-008, RM-F-009, RM-F-010, RM-F-011 | RM-C-006 | REL-003, REL-001 on the tag; zero unexplained FAIL; zero BLOCKED; final harness run committed | — | blocked (M5 gate)

## Detailed Backlog
ID | Workstream | Epic | Milestone | Deliverable | Description | Current State | Target State | Priority | Dependency IDs | Dependency Type | Blocks | Can Run in Parallel | Independent / Dependent | Critical Path | Owner / Required Role | Required Environment | Required Infrastructure | Required Permissions | Required API Keys / Credentials | Estimated Effort | Risk | Acceptance Criteria | Harness Test IDs | Exit Gate | Status | Progress % | Evidence / Artifact | Notes | Day 1 | Why does this exist? | What does it unlock?
RM-A-001 | A Verification & Evidence | EP-3 Evidence over assertion | M1 | `scripts/harness.sh` (from harness.md §8) plus `docs/evolution/evidence/` convention (`*.wav` ignored) | One command per checkpoint; writes summary.tsv and per-check logs. The T0 dry run of the embedded script already reproduced the recorded verdicts. | Runner exists only as a code block in harness.md; T0 evidence is in a session scratch directory | HARNESS-OBS-002 PASS at T1 | P0 | — | — | RM-A-002, RM-A-004, RM-A-005, every checkpoint sign-off | yes | independent | no (enabling) | maintainer | reference | bash, jq, gh, uv, node | push | gh token for CI rows | S | none | `scripts/harness.sh T1` produces summary.tsv with all 59 IDs; PASS/FAIL agree with manual runs | HARNESS-OBS-002, HARNESS-GATE-006, HARNESS-PERF-001, HARNESS-SEC-002, HARNESS-ACC-002, HARNESS-SEC-001 | M1 observability gate | complete | 100 | commit a8e8690 (+ hardening 4157c74): scripts/harness.sh; evidence/T1, T2 bundles | Day 1. | yes | Progress must be measured by execution, not by prose. | objective checkpoint decisions
RM-A-002 | A Verification & Evidence | EP-3 Evidence over assertion | M1 | `docs/evolution/{report.md,roadmap.xlsx,harness.md}` committed with the T0 baseline; T0 evidence summary re-created from the runner | These three artifacts exist in the working tree (this assessment) but are uncommitted, like the repair itself. | Files written 2026-09-05, uncommitted | Committed on the release branch; evidence/T0/summary.tsv tracked | P1 | RM-A-001 (for the evidence dir); RM-C-001 (sequencing) | soft | — | yes | dependent | no | maintainer | reference | git | push | none | XS | none | `git ls-files docs/evolution` lists the three files and evidence/T0 | HARNESS-OBS-002 | M1 | complete | 100 | commits 2f4ca49, a8e8690: docs/evolution + evidence/T0 committed |  | yes | An assessment nobody can find later did not happen. | —
RM-B-001 | B Portability & CI | EP-2 Make the gate real | M1 | Package and tests import on Python 3.10: `datetime.UTC` → `timezone.utc` in audioforge/sample_catalog/licenses.py; `tomllib` in tests/test_lark_parser.py replaced or guarded | Pre-existing since commit f1c34a0 (2026-06-13); undetected because CI never ran. `requires-python >= 3.10` and the CI matrix promise 3.10. | `make check` under 3.10 aborts at manifest-check with ImportError | HARNESS-PORT-001 PASS | P0 | — | — | RM-B-003, RM-B-004, HARNESS-CI-002 → RM-C-005 | yes | independent | yes | maintainer | py310 venv (uv) | uv-managed CPython 3.10 | push | none | XS | R3 further 3.10 incompatibilities surface | `make check PYTHON=<py310>` exit 0; grep finds no other 3.11-only constructs | HARNESS-PORT-001, HARNESS-CI-002 | M1 portability gate | complete | 100 | commit 5a3244f; evidence/T1 HARNESS-PORT-001 | Two-line fix; the finding matters more than the fix. | yes | The declared Python floor is false today. | a green CI matrix
RM-B-002 | B Portability & CI | EP-2 Make the gate real | M1 (diagnosed) / M3 (green) | Root cause of `startup_failure` on every GitHub Actions run identified and fixed; at least one job executes | 7/7 runs since 2026-07-04 fail at startup with 0 jobs. YAML parses; Actions enabled; repo private. Most probable cause: Actions billing / spending limit on a private repository (unconfirmed: billing API needs the `user` token scope). Check Settings → Billing → Actions, and Settings → Actions → General. | HARNESS-CI-001 FAIL; root cause unconfirmed | HARNESS-CI-001 PASS | P0 | — | — | HARNESS-CI-002/003/004 → RM-C-005, RM-D-001 remote validation | yes | independent | yes | admin | GitHub web UI / gh with `user` scope | GitHub Actions minutes or an alternative runner | repository admin; billing visibility | gh auth refresh -s user (if diagnosing via API) | S (unknown until diagnosed) | R2 remedy costs money or requires a self-hosted runner | a run with total_count ≥ 1 jobs; cause and remedy recorded in docs/evolution/evidence/T1/ci-root-cause.md | HARNESS-CI-001, HARNESS-CI-002, HARNESS-CI-004 | M1 (diagnosis), M3 CI gate | blocked | 30 | diagnosed: evidence/T1/ci-root-cause.md (account-level Actions condition inferred; billing unreadable with this token); repository-admin action required | Decision D4 in report.md: fix billing vs self-hosted runner vs alternative CI. | yes | Every `[Enforced]` rule in codebase-standards.md is advisory while this holds. | remote evidence for merge
RM-C-001 | C Integration & Release | EP-1 Ship engine 3.0.0 | M1 | Release branch `release/engine-3.0.0` with the repair committed as a reviewed series and pushed to origin | Commit the 45 modified + 12 untracked files in coherent commits (semantics, arrangement, harmony/performance, docs/ADR/ledger, goldens + version bump) and push. Nothing else is safe until a second copy exists. | Uncommitted working tree on top of 60c0fd5; origin last pushed 2026-07-05; single copy on one machine | Branch on origin; `git status --porcelain` empty; branch head == origin head | P0 | — | — | RM-C-002, RM-C-003, RM-C-004, RM-A-003, RM-D-001…006 (sequencing), RM-E-001…005 (sequencing), RM-F-001…011 | yes, with RM-B-001, RM-B-002, RM-A-001 | independent | yes | maintainer | reference | git, GitHub remote | push to origin | git credentials (present: gh logged in as pedroanisio) | S | R1 data loss; R4 audible change lands on main before docs are read (mitigated by branch) | HARNESS-VCS-001 and HARNESS-VCS-002 PASS for the branch; every commit message follows conventional commits; no generated artifact hand-edited | HARNESS-VCS-001, HARNESS-VCS-002 | M1 data-safety gate | complete | 100 | commits 4a75778, 2f4ca49 on release/engine-3.0.0; pushed; evidence/T1 HARNESS-VCS-001/002 | Day 1. Do this before RM-B-001 so the fix is a follow-up commit on the same branch. | yes | The only copy of four hours of engine work is an uncommitted tree. | review, CI, merge, listening review (needs a SHA), everything downstream
RM-C-002 | C Integration & Release | EP-1 Ship engine 3.0.0 | M1 | `uv.lock` regenerated and committed | Run `uv lock`; the lockfile still records audioforge 2.16.0 although pyproject says 3.0.0. | `uv lock --check` fails | `uv lock --check` exit 0 | P1 | RM-C-001 | sequencing (same branch) | RM-B-004 | yes | dependent | no | maintainer | reference | uv 0.10.9 | push | none | XS | none | HARNESS-REL-004 PASS | HARNESS-REL-004 | M1 | complete | 100 | commit 5a3244f (uv.lock 3.0.0); evidence/T1 HARNESS-REL-004 | Discovered because a docs build rewrote the lockfile during the assessment; the edit was reverted and recorded as a finding. | yes | A lockfile that disagrees with the manifest makes `uv run` non-reproducible. | RM-B-004 gate addition
RM-A-004 | A Verification & Evidence | EP-3 Evidence over assertion | M2 | Acceptance-bundle reproducibility check in the runner (two runs, identical output hashes) | Already true at T0 (7/7 identical); make it a standing assertion. | Manual check only | HARNESS-ACC-004 PASS in every bundle | P2 | RM-A-001 | hard | — | yes | dependent | no | maintainer | reference | — | none | none | XS | none | ACC-004 line in summary.tsv | HARNESS-ACC-004 | M2 | complete | 100 | evidence/T2 HARNESS-ACC-004 |  | no | The review page is evidence only if it is reproducible. | —
RM-B-003 | B Portability & CI | EP-2 Make the gate real | M2 | Local matrix run recorded: `make check` under 3.10, 3.11, 3.12 with cross-env golden behaviour noted | T0 already shows 3.11 and 3.12 green with goldens byte-identical under different numpy/scipy; 3.10 must be re-run after RM-B-001. | 3.10 FAIL, 3.11 PASS, 3.12 PASS | PORT-001…004 PASS on the branch head | P1 | RM-B-001 | hard | — | yes | dependent | no | maintainer | py310/py311/py312 venvs | uv | none | none | S | none | three exit-0 logs in evidence/T2 | HARNESS-PORT-001, HARNESS-PORT-002, HARNESS-PORT-003, HARNESS-PORT-004 | M2 | complete | 100 | evidence/T2 HARNESS-PORT-001…004 (3.10/3.11/3.12 green on the branch head) |  | no | The CI matrix has never run; local matrix is the substitute until it does. | confidence for RM-C-005
RM-D-004 | D Governance & Records | EP-4 Records tell the truth | M2 (wording) / M4 (final) | ADR-0001 amended: randomness is rooted in `performance_hash(seed, variant)`, spec hash remains the contract identity, pointer to ADR-0007; ADR-0007 status reads Accepted until merged, Implemented after | ADR-0001 still states all randomness derives from the spec hash; the repair changed that. ADR-0007 claims 'implemented' for uncommitted code. | GOV-004 FAIL, GOV-006 FAIL | both PASS | P1 | — | — | RM-C-005 (M2 gate) | yes | independent | no | maintainer | reference | — | push | none | XS | R8 readers rely on the wrong determinism model | GOV-004, GOV-006 PASS; tests/test_docs_site.py ADR checks green | HARNESS-GOV-004, HARNESS-GOV-006 | M2 contract gate | complete | 100 | commits 09e1dfa, 4157c74; evidence/T2 HARNESS-GOV-004/006 |  | yes | Two accepted ADRs currently contradict each other on the determinism model. | —
RM-D-005 | D Governance & Records | EP-4 Records tell the truth | M2 | docs/index.md determinism sentence matches README and ADR-0007 (environment-scoped reproducibility, no 'forever') | The docs-site home page still promises byte-identical audio every render, forever; README was corrected, index.md was not. | GOV-005 FAIL | PASS | P2 | — | — | — | yes | independent | no | maintainer | reference | — | push | none | XS | none | GOV-005 PASS; mkdocs strict green | HARNESS-GOV-005, HARNESS-GATE-004 | M2 | complete | 100 | commit 09e1dfa; evidence/T2 HARNESS-GOV-005 |  | yes | The first page an outsider reads makes a claim the engine no longer makes. | —
RM-D-006 | D Governance & Records | EP-4 Records tell the truth | M2 | `.agent-tasks/.current_task` cleared or repointed; pointer semantics documented in AGENTS.md §5 | The pointer names an archived task with status failed. | GOV-007 FAIL | PASS | P3 | — | — | — | yes | independent | no | maintainer | reference | — | none | none | XS | none | GOV-007 PASS | HARNESS-GOV-007 | M2 (non-blocking) | complete | 100 | commit 09e1dfa; evidence/T2 HARNESS-GOV-007 | Non-blocking hygiene. | no | Coordination state that lies costs the next agent time. | —
RM-E-001 | E Contract Hardening | EP-5 Inspectable contract | M2 | `ambiguous_harmony`, `unrecognized_harmony`, `loop_boundary_tail` and the analysis codes (`dead_air`, `mono_image`, `low_foundation_weak`, `very_bright`, …) registered in capabilities.py; manifest and DIAGNOSTIC_CODES.md regenerated; a test asserts emitted ⊆ registered | The registry documents 29 codes and claims 'a new code cannot land undocumented'; the repair added three codes that are not in it. | CON-001 FAIL | PASS | P1 | — | — | RM-E-002, RM-C-005 (M2 gate) | yes | independent | no | maintainer | reference | — | push | none | S | R7 agents parse prose | CON-001 PASS; manifest-check green; new test in tests/ | HARNESS-CON-001 | M2 contract gate | complete | 100 | commits 901191c, 4157c74 (40 registered codes); evidence/T2 HARNESS-CON-001 | Generator-owned artifacts: never hand-edit. | yes | PURPOSE: failure must be loud and local; a code the manifest does not list is neither. | RM-E-002
RM-E-003 | E Contract Hardening | EP-5 Inspectable contract | M2 | `audioforge verify` accepts `.af` (compiles first) or returns a structured diagnostic naming the expected input; documented exit codes | Today an .af path yields `Error: Expecting value: line 1 column 1 (char 0)` exit 1. | CON-003 FAIL | PASS | P2 | — | — | — | yes | independent | no | maintainer | reference | — | push | none | XS | none | CON-003 PASS; AGENTS.md verb table updated; tests/test_cli.py case | HARNESS-CON-003 | M2 | complete | 100 | commit cd06e1c; evidence/T2 HARNESS-CON-003 |  | yes | A raw decoder error is a user-facing traceback by another name (DSL_GAP_SPEC §3.3). | —
RM-E-004 | E Contract Hardening | EP-5 Inspectable contract | M2 | `validate_spec` (or the SDK/agent facade) copies on entry so callers' specs are never rewritten; regression test; docstring states the guarantee | With `score.repeats`, validate_spec rewrites the caller's dict in place (2.0 s → 4.0 s, repeats consumed) and run_tool('validate') does the same to an agent's request. Decision D2: copy in validate_spec vs copy at the facade vs document the mutation. | CON-004 FAIL | PASS | P1 | — | — | RM-C-005 (M2 gate) | yes | independent | no | maintainer + reviewer | reference | — | push | none | S | R6 agents render a spec they did not author; render cost of an extra deepcopy | CON-004 PASS; GATE-001 green; goldens unchanged | HARNESS-CON-004, HARNESS-GATE-003 | M2 contract gate | complete | 100 | commit aa3c9d6; evidence/T2 HARNESS-CON-004 | Recommended: deepcopy at the top of validate_spec; cost is negligible next to rendering. | yes | IR is truth (ADR-0003) only if the IR an agent holds is the IR that renders. | —
RM-F-001 | F Musical semantics (ledger) | EP-1 Ship engine 3.0.0 | M2 (branch) → M4 (CI) → M6 (released) | Ledger row A1: Instrument gain applied exactly once, including virtual sections | Implemented in the working tree (render.py gain path, sampler.py). Independently reproduced at T0: the harness rows pass on the working tree and the acceptance case fails on engine 2.16.0. Completion is gated on commit, CI and release, not on the code. | implemented, locally verified by the author, independently reproduced on the reference machine (T0); uncommitted | released: harness rows PASS on the tagged commit under CI | P0 | RM-C-001 (commit), RM-C-005 (merge), RM-C-006 (tag) | hard (delivery chain) | — | n/a (done) | dependent | rides the critical path | maintainer | reference + CI | — | — | — | done (verification only) | R4 audible change for existing specs | HARNESS-AUD-001, HARNESS-ACC-001 PASS on branch (T2), on CI (T3/T4), on tag (T6); ledger status advances only with evidence | HARNESS-AUD-001, HARNESS-ACC-001 | M2 test gate; M4 migration gate; M6 release gate | independently-reproduced | 70 | docs/MUSICAL_CORRECTNESS.md row A1; evidence/T0 (this assessment); committed as 4a75778 on release/engine-3.0.0; evidence/T2 (branch head) PASS; awaits CI (ci-verified) and tag (released) | Progress scale: implemented 40 · locally-verified 60 · independently-reproduced 70 · ci-verified 90 · released 100. | no | September review finding behind ledger row A1. | —
RM-F-002 | F Musical semantics (ledger) | EP-1 Ship engine 3.0.0 | M2 (branch) → M4 (CI) → M6 (released) | Ledger row A2: Note duration is gate time; release follows note-off for synth and samples | Implemented in the working tree (synth.note_adsr, sequencer.py, sampler.py). Independently reproduced at T0: the harness rows pass on the working tree and the acceptance case fails on engine 2.16.0. Completion is gated on commit, CI and release, not on the code. | implemented, locally verified by the author, independently reproduced on the reference machine (T0); uncommitted | released: harness rows PASS on the tagged commit under CI | P0 | RM-C-001 (commit), RM-C-005 (merge), RM-C-006 (tag) | hard (delivery chain) | — | n/a (done) | dependent | rides the critical path | maintainer | reference + CI | — | — | — | done (verification only) | R4 audible change for existing specs | HARNESS-AUD-002, HARNESS-ACC-001 PASS on branch (T2), on CI (T3/T4), on tag (T6); ledger status advances only with evidence | HARNESS-AUD-002, HARNESS-ACC-001 | M2 test gate; M4 migration gate; M6 release gate | independently-reproduced | 70 | docs/MUSICAL_CORRECTNESS.md row A2; evidence/T0 (this assessment); committed as 4a75778 on release/engine-3.0.0; evidence/T2 (branch head) PASS; awaits CI (ci-verified) and tag (released) | Progress scale: implemented 40 · locally-verified 60 · independently-reproduced 70 · ci-verified 90 · released 100. | no | September review finding behind ledger row A2. | —
RM-F-003 | F Musical semantics (ledger) | EP-1 Ship engine 3.0.0 | M2 (branch) → M4 (CI) → M6 (released) | Ledger row A3: Rate-adaptive anti-alias resampling preserving in-band pitch and level | Implemented in the working tree (sampler._sinc_read). Independently reproduced at T0: the harness rows pass on the working tree and the acceptance case fails on engine 2.16.0. Completion is gated on commit, CI and release, not on the code. | implemented, locally verified by the author, independently reproduced on the reference machine (T0); uncommitted | released: harness rows PASS on the tagged commit under CI | P0 | RM-C-001 (commit), RM-C-005 (merge), RM-C-006 (tag) | hard (delivery chain) | — | n/a (done) | dependent | rides the critical path | maintainer | reference + CI | — | — | — | done (verification only) | R4 audible change for existing specs | HARNESS-AUD-003, HARNESS-ACC-001 PASS on branch (T2), on CI (T3/T4), on tag (T6); ledger status advances only with evidence | HARNESS-AUD-003, HARNESS-ACC-001 | M2 test gate; M4 migration gate; M6 release gate | independently-reproduced | 70 | docs/MUSICAL_CORRECTNESS.md row A3; evidence/T0 (this assessment); committed as 4a75778 on release/engine-3.0.0; evidence/T2 (branch head) PASS; awaits CI (ci-verified) and tag (released) | Progress scale: implemented 40 · locally-verified 60 · independently-reproduced 70 · ci-verified 90 · released 100. | no | September review finding behind ledger row A3. | —
RM-F-004 | F Musical semantics (ledger) | EP-1 Ship engine 3.0.0 | M2 (branch) → M4 (CI) → M6 (released) | Ledger row A4: Mastering preserves quiet levels; explicit normalization; ceiling includes fades and intersample peaks | Implemented in the working tree (render._finish, dynamics.py, schema.py). Independently reproduced at T0: the harness rows pass on the working tree and the acceptance case fails on engine 2.16.0. Completion is gated on commit, CI and release, not on the code. | implemented, locally verified by the author, independently reproduced on the reference machine (T0); uncommitted | released: harness rows PASS on the tagged commit under CI | P0 | RM-C-001 (commit), RM-C-005 (merge), RM-C-006 (tag) | hard (delivery chain) | — | n/a (done) | dependent | rides the critical path | maintainer | reference + CI | — | — | — | done (verification only) | R4 audible change for existing specs | HARNESS-AUD-004, HARNESS-ACC-001 PASS on branch (T2), on CI (T3/T4), on tag (T6); ledger status advances only with evidence | HARNESS-AUD-004, HARNESS-ACC-001 | M2 test gate; M4 migration gate; M6 release gate | independently-reproduced | 70 | docs/MUSICAL_CORRECTNESS.md row A4; evidence/T0 (this assessment); committed as 4a75778 on release/engine-3.0.0; evidence/T2 (branch head) PASS; awaits CI (ci-verified) and tag (released) | Progress scale: implemented 40 · locally-verified 60 · independently-reproduced 70 · ci-verified 90 · released 100. | no | September review finding behind ledger row A4. | —
RM-F-005 | F Musical semantics (ledger) | EP-1 Ship engine 3.0.0 | M2 (branch) → M4 (CI) → M6 (released) | Ledger row M1: Evidence-based chord identity, preserved sevenths, ambiguity reported, key-aware extensions, bounded voice leading | Implemented in the working tree (harmony.py, dsl.py). Independently reproduced at T0: the harness rows pass on the working tree and the acceptance case fails on engine 2.16.0. Completion is gated on commit, CI and release, not on the code. | implemented, locally verified by the author, independently reproduced on the reference machine (T0); uncommitted | released: harness rows PASS on the tagged commit under CI | P0 | RM-C-001 (commit), RM-C-005 (merge), RM-C-006 (tag) | hard (delivery chain) | — | n/a (done) | dependent | rides the critical path | maintainer | reference + CI | — | — | — | done (verification only) | R4 audible change for existing specs | HARNESS-MUS-001, HARNESS-ACC-001 PASS on branch (T2), on CI (T3/T4), on tag (T6); ledger status advances only with evidence | HARNESS-MUS-001, HARNESS-ACC-001 | M2 test gate; M4 migration gate; M6 release gate | independently-reproduced | 70 | docs/MUSICAL_CORRECTNESS.md row M1; evidence/T0 (this assessment); committed as 4a75778 on release/engine-3.0.0; evidence/T2 (branch head) PASS; awaits CI (ci-verified) and tag (released) | Progress scale: implemented 40 · locally-verified 60 · independently-reproduced 70 · ci-verified 90 · released 100. | no | September review finding behind ledger row M1. | —
RM-F-006 | F Musical semantics (ledger) | EP-1 Ship engine 3.0.0 | M2 (branch) → M4 (CI) → M6 (released) | Ledger row M2: Phrase and performance decisions from authored structure; no fabricated cadences; conductor clock | Implemented in the working tree (performance.py, dsl.py). Independently reproduced at T0: the harness rows pass on the working tree and the acceptance case fails on engine 2.16.0. Completion is gated on commit, CI and release, not on the code. | implemented, locally verified by the author, independently reproduced on the reference machine (T0); uncommitted | released: harness rows PASS on the tagged commit under CI | P0 | RM-C-001 (commit), RM-C-005 (merge), RM-C-006 (tag) | hard (delivery chain) | — | n/a (done) | dependent | rides the critical path | maintainer | reference + CI | — | — | — | done (verification only) | R4 audible change for existing specs | HARNESS-MUS-002, HARNESS-ACC-001 PASS on branch (T2), on CI (T3/T4), on tag (T6); ledger status advances only with evidence | HARNESS-MUS-002, HARNESS-ACC-001 | M2 test gate; M4 migration gate; M6 release gate | independently-reproduced | 70 | docs/MUSICAL_CORRECTNESS.md row M2; evidence/T0 (this assessment); committed as 4a75778 on release/engine-3.0.0; evidence/T2 (branch head) PASS; awaits CI (ci-verified) and tag (released) | Progress scale: implemented 40 · locally-verified 60 · independently-reproduced 70 · ci-verified 90 · released 100. | no | September review finding behind ledger row M2. | —
RM-F-007 | F Musical semantics (ledger) | EP-1 Ship engine 3.0.0 | M2 (branch) → M4 (CI) → M6 (released) | Ledger row M3: Explicit technique fidelity; strict routing rejects approximations; planner/runtime parity | Implemented in the working tree (plan.py, schema.TECHNIQUES, sampler.py). Independently reproduced at T0: the harness rows pass on the working tree and the acceptance case fails on engine 2.16.0. Completion is gated on commit, CI and release, not on the code. | implemented, locally verified by the author, independently reproduced on the reference machine (T0); uncommitted | released: harness rows PASS on the tagged commit under CI | P0 | RM-C-001 (commit), RM-C-005 (merge), RM-C-006 (tag) | hard (delivery chain) | — | n/a (done) | dependent | rides the critical path | maintainer | reference + CI | — | — | — | done (verification only) | R4 audible change for existing specs | HARNESS-MUS-003 PASS on branch (T2), on CI (T3/T4), on tag (T6); ledger status advances only with evidence | HARNESS-MUS-003 | M2 test gate; M4 migration gate; M6 release gate | independently-reproduced | 70 | docs/MUSICAL_CORRECTNESS.md row M3; evidence/T0 (this assessment); committed as 4a75778 on release/engine-3.0.0; evidence/T2 (branch head) PASS; awaits CI (ci-verified) and tag (released) | Progress scale: implemented 40 · locally-verified 60 · independently-reproduced 70 · ci-verified 90 · released 100. | no | September review finding behind ledger row M3. | —
RM-F-008 | F Musical semantics (ledger) | EP-1 Ship engine 3.0.0 | M2 (branch) → M4 (CI) → M6 (released) | Ledger row M4: Executable repeats; meter/pickup semantics; measured loop safety | Implemented in the working tree (arrangement.py, schema.py, analysis.loop_boundary_report). Independently reproduced at T0: the harness rows pass on the working tree and the acceptance case fails on engine 2.16.0. Completion is gated on commit, CI and release, not on the code. | implemented, locally verified by the author, independently reproduced on the reference machine (T0); uncommitted | released: harness rows PASS on the tagged commit under CI | P0 | RM-C-001 (commit), RM-C-005 (merge), RM-C-006 (tag) | hard (delivery chain) | — | n/a (done) | dependent | rides the critical path | maintainer | reference + CI | — | — | — | done (verification only) | R4 audible change for existing specs | HARNESS-MUS-004, HARNESS-ACC-001 PASS on branch (T2), on CI (T3/T4), on tag (T6); ledger status advances only with evidence | HARNESS-MUS-004, HARNESS-ACC-001 | M2 test gate; M4 migration gate; M6 release gate | independently-reproduced | 70 | docs/MUSICAL_CORRECTNESS.md row M4; evidence/T0 (this assessment); committed as 4a75778 on release/engine-3.0.0; evidence/T2 (branch head) PASS; awaits CI (ci-verified) and tag (released) | Progress scale: implemented 40 · locally-verified 60 · independently-reproduced 70 · ci-verified 90 · released 100. | no | September review finding behind ledger row M4. | —
RM-F-009 | F Musical semantics (ledger) | EP-1 Ship engine 3.0.0 | M2 (branch) → M4 (CI) → M6 (released) | Ledger row M5: Stable performance identity under mix edits; explicit seeds; stable event IDs | Implemented in the working tree (determinism.performance_hash, note_seed_paths). Independently reproduced at T0: the harness rows pass on the working tree and the acceptance case fails on engine 2.16.0. Completion is gated on commit, CI and release, not on the code. | implemented, locally verified by the author, independently reproduced on the reference machine (T0); uncommitted | released: harness rows PASS on the tagged commit under CI | P0 | RM-C-001 (commit), RM-C-005 (merge), RM-C-006 (tag) | hard (delivery chain) | — | n/a (done) | dependent | rides the critical path | maintainer | reference + CI | — | — | — | done (verification only) | R4 audible change for existing specs | HARNESS-MUS-005, HARNESS-OBS-001 PASS on branch (T2), on CI (T3/T4), on tag (T6); ledger status advances only with evidence | HARNESS-MUS-005, HARNESS-OBS-001 | M2 test gate; M4 migration gate; M6 release gate | independently-reproduced | 70 | docs/MUSICAL_CORRECTNESS.md row M5; evidence/T0 (this assessment); committed as 4a75778 on release/engine-3.0.0; evidence/T2 (branch head) PASS; awaits CI (ci-verified) and tag (released) | Progress scale: implemented 40 · locally-verified 60 · independently-reproduced 70 · ci-verified 90 · released 100. | no | September review finding behind ledger row M5. | —
RM-F-010 | F Musical semantics (ledger) | EP-1 Ship engine 3.0.0 | M2 (branch) → M4 (CI) → M6 (released) | Ledger row M6: Context-aware analysis: observations always, recommendations under declared expectations | Implemented in the working tree (analysis.py, agent_tools.py, mcp/server.py). Independently reproduced at T0: the harness rows pass on the working tree and the acceptance case fails on engine 2.16.0. Completion is gated on commit, CI and release, not on the code. | implemented, locally verified by the author, independently reproduced on the reference machine (T0); uncommitted | released: harness rows PASS on the tagged commit under CI | P0 | RM-C-001 (commit), RM-C-005 (merge), RM-C-006 (tag) | hard (delivery chain) | — | n/a (done) | dependent | rides the critical path | maintainer | reference + CI | — | — | — | done (verification only) | R4 audible change for existing specs | HARNESS-MUS-006 PASS on branch (T2), on CI (T3/T4), on tag (T6); ledger status advances only with evidence | HARNESS-MUS-006 | M2 test gate; M4 migration gate; M6 release gate | independently-reproduced | 70 | docs/MUSICAL_CORRECTNESS.md row M6; evidence/T0 (this assessment); committed as 4a75778 on release/engine-3.0.0; evidence/T2 (branch head) PASS; awaits CI (ci-verified) and tag (released) | Progress scale: implemented 40 · locally-verified 60 · independently-reproduced 70 · ci-verified 90 · released 100. | no | September review finding behind ledger row M6. | —
RM-F-011 | F Musical semantics (ledger) | EP-1 Ship engine 3.0.0 | M2 (branch) → M4 (CI) → M6 (released) | Ledger row G1: All public and generated surfaces agree with the final behaviour (schema, manifest, docs, versions, goldens) | Implemented in the working tree (docs/ir.schema.json, capability-manifest.json, tests/golden/audio.lock.json, version.py). Independently reproduced at T0: the harness rows pass on the working tree and the acceptance case fails on engine 2.16.0. Completion is gated on commit, CI and release, not on the code. | implemented, locally verified by the author, independently reproduced on the reference machine (T0); uncommitted | released: harness rows PASS on the tagged commit under CI | P0 | RM-C-001 (commit), RM-C-005 (merge), RM-C-006 (tag) | hard (delivery chain) | — | n/a (done) | dependent | rides the critical path | maintainer | reference + CI | — | — | — | done (verification only) | R4 audible change for existing specs | HARNESS-GATE-001, HARNESS-GATE-002, HARNESS-GATE-003, HARNESS-GATE-004, HARNESS-GATE-005, HARNESS-REL-001, HARNESS-MIG-001, HARNESS-MIG-002, HARNESS-MIG-003 PASS on branch (T2), on CI (T3/T4), on tag (T6); ledger status advances only with evidence | HARNESS-GATE-001, HARNESS-GATE-002, HARNESS-GATE-003, HARNESS-GATE-004, HARNESS-GATE-005, HARNESS-REL-001, HARNESS-MIG-001, HARNESS-MIG-002, HARNESS-MIG-003 | M2 test gate; M4 migration gate; M6 release gate | independently-reproduced | 70 | docs/MUSICAL_CORRECTNESS.md row G1; evidence/T0 (this assessment); committed as 4a75778 on release/engine-3.0.0; evidence/T2 (branch head) PASS; awaits CI (ci-verified) and tag (released) | Progress scale: implemented 40 · locally-verified 60 · independently-reproduced 70 · ci-verified 90 · released 100. | no | September review finding behind ledger row G1. | —
RM-B-004 | B Portability & CI | EP-2 Make the gate real | M3 | `make check` gains `uv lock --check` and a Python-floor import smoke (`python3.10 -c 'import audioforge.capabilities'` via uv) so PORT-001 and REL-004 cannot regress; tests/test_makefile_targets.py updated | Enabling work: turns two T0 findings into enforced rules per codebase-standards.md. | Neither check exists in the gate | both targets in `check:`; standards table rows flip to [Enforced] | P2 | RM-B-001, RM-C-002 | hard | — | yes | dependent | no | maintainer | reference | uv on CI runners | push | none | S | R13 gate time grows (budget 300 s) | make check exit 0 with new targets; PERF-001 still PASS; codebase-standards.md updated | HARNESS-REL-004, HARNESS-PORT-001, HARNESS-PERF-001 | M3 contract gate | complete | 100 | commit 9892e60: make lock-check + floor-check; ci.yml installs uv |  | no | A finding that is not gated recurs. | —
RM-C-003 | C Integration & Release | EP-1 Ship engine 3.0.0 | M3 | Pull request with an independent approving review; every finding fixed or declined with a reason | Open a PR from the release branch; run `/code-review` (or equivalent) and a human read of the semantic changes (render.py, sampler.py, sequencer.py, arrangement.py, harmony.py, performance.py, schema.py); track findings to closure. | No branch, no PR; the author (an agent) verified its own work | HARNESS-VCS-003 PASS | P0 | RM-C-001; soft: RM-B-001, RM-B-002 (CI signal helps the reviewer) | hard on C-001; soft on B-* | RM-C-005 | yes, with RM-D-*, RM-E-* | dependent | yes | reviewer | reference or reviewer's machine | GitHub PR | review permission on the repo | gh token | M | R12 single-maintainer review capacity | ≥1 APPROVED review; review notes attached to the PR; RM-E-004 decision recorded in the review | HARNESS-VCS-003 | M3 review gate | in-progress | 80 | PR #1: eight-pass agent code review complete; 9 reproduced defects fixed on the branch (3d19d26 intent round trip + unique layer names; e5decf6 repeat slivers, groove slot under swing, clip-aware activity; 46ef6cd shared validators, explicit fidelity, helper reuse; cd55a73 tone freq:, cutdowns not loop-gated); 9 accepted findings deferred to BL-036..BL-044; review comment on the PR; human approval pending (operator) | Under PALS's law the author's own gate run is not verification. | no | No independent reader has examined ~2 200 changed lines of audio semantics. | merge
RM-D-001 | D Governance & Records | EP-4 Records tell the truth | M3 | Backlog registry items for the musical-correctness release (an epic plus one item per ledger group A, M, G) with `evidence_checks` on the new tests and docs; `docs/BACKLOG.md` re-rendered; governance script green | docs/backlog.yml is the declared system of record for status, yet it contains no item for the largest change since 2.16.0. | 0 items mention the repair, ADR-0007 or 3.0.0 | HARNESS-GOV-001 PASS | P1 | RM-C-001 (sequencing) | sequencing | RM-C-005 (M3 gate) | yes | independent (content) | no | maintainer | reference | node 24 | push | none | S | R14 governance workflow also broken remotely | items validate; each has evidence_checks; tags carry ADR-0007 | HARNESS-GOV-001, HARNESS-GATE-005, HARNESS-CI-004 | M3 contract gate | complete | 100 | commits c49c46c (BL-032..BL-035), 2178916 (BL-036..BL-044 from the review); evidence/T2 HARNESS-GOV-001 |  | no | A registry that omits the biggest change cannot be the system of record. | status tracking in the repo's own tooling
RM-D-002 | D Governance & Records | EP-4 Records tell the truth | M3 | BL-004, BL-010, BL-011, BL-012, BL-013, BL-014 set to `done` with evidence_checks (AF-R03, R09, R10, R11, R12, R13 are in git log) | Registry says `ready` for six delivered items; the roadmap's own rule says the registry wins on status, so it is currently wrong. | six stale `ready` statuses | HARNESS-GOV-002 PASS | P2 | — | — | — | yes | independent | no | maintainer | reference | node | push | none | XS | none | GOV-002 PASS; governance script green | HARNESS-GOV-002 | M3 | complete | 100 | commit c49c46c; evidence/T2 HARNESS-GOV-002 |  | yes | Stale statuses train readers to ignore the registry. | —
RM-D-003 | D Governance & Records | EP-4 Records tell the truth | M3 (then each checkpoint) | Ledger `Status` column uses the staged vocabulary (implemented → locally-verified → independently-reproduced → ci-verified → released), every row cites its HARNESS IDs, pre-existing regression guards are labelled, and a listening row is added | Twelve rows read `Verified` on the author's own local run. Replace with the harness vocabulary and advance statuses only from evidence bundles. | 12 × `Verified`; test_performance_model.py cited but unchanged | HARNESS-GOV-003 and GOV-008 PASS | P1 | — | — | RM-C-006 (final 'released' statuses) | yes | independent | no | maintainer | reference | — | push | none | XS | none | 0 occurrences of '¦ Verified ¦'; ≥12 HARNESS- citations; statuses match the latest evidence bundle | HARNESS-GOV-003, HARNESS-GOV-008 | M3 contract gate; M6 release gate | complete | 100 | commit baecfaa; evidence/T2 HARNESS-GOV-003 (statuses advance again at T4/T6) |  | yes | 'Verified' without an independent, remote, committed run is the exact failure PALS's law names. | honest release notes
RM-E-002 | E Contract Hardening | EP-5 Inspectable contract | M3 | `Diagnostic.code` field populated by compiler, validator, planner and analysis; exposed in agent_tools and MCP envelopes; ADR-0008 (public-surface change); MCP contract test asserts the field | Codes are currently embedded in message text. 3.0.0 is the right release for an additive surface change; alternative is ADR-0008 recording deferral to 3.1 with a waiver (decision D1). | CON-002 FAIL | PASS or ADR-0008 deferral + waiver | P1 | RM-E-001 | hard | RM-C-005 (M3 architecture gate: decision required) | yes | dependent | no (gate-blocking, waivable) | maintainer + reviewer | reference | — | push | none | M | R13 coverage dip; envelope consumers | CON-002 PASS; ADR-0008 accepted; tests/test_mcp_contract.py green | HARNESS-CON-002 | M3 architecture gate | complete | 100 | commit 52b1eac + ADR-0008; evidence/T2 HARNESS-CON-002 |  | no | Agents are the primary consumer and cannot branch on prose. | deterministic agent repair loops (DSL_GAP_SPEC G7)
RM-C-004 | C Integration & Release | EP-1 Ship engine 3.0.0 | M4 | `CHANGELOG.md` with one dated `[3.0.0]` section containing Track E (AF-R01…R13) and the musical fixes; `docs/RELEASE_NOTES.md` final | Everything since tag engine-2.16.0 ships as 3.0.0; today Track E sits under [Unreleased] while [3.0.0] lists only the fixes. Keep `bump_version --check` green. | Split sections, no date | HARNESS-REL-002 PASS | P1 | RM-C-001 | sequencing | RM-C-006 | yes | dependent | no | maintainer | reference | — | push | none | XS | none | HARNESS-REL-002 and HARNESS-REL-001 PASS | HARNESS-REL-002, HARNESS-REL-001 | M4 migration gate | complete | 100 | commit 3adfeb9; evidence/T2 HARNESS-REL-002 | Decision D5 in report.md recommends folding Track E into 3.0.0. | no | The changelog is the migration message users read first. | tagging
RM-C-005 | C Integration & Release | EP-1 Ship engine 3.0.0 | M4 | Release branch merged into `main` with the `ci` workflow green on Python 3.10/3.11/3.12 for the merge commit | Merge only on remote evidence. Re-run GATE-001…005 on main after merge. | Nothing merged; CI has never executed a job | HARNESS-VCS-004 and HARNESS-CI-003 PASS | P0 | RM-C-003, RM-B-001, RM-B-002, RM-E-001, RM-E-003, RM-E-004, RM-D-001, RM-D-002, RM-D-003, RM-D-004, RM-D-005; RM-E-002 or its ADR-0008 deferral | hard (gates M2, M3) | RM-C-006, RM-F-001…011 completion | no | dependent | yes | maintainer | GitHub | GitHub Actions | merge to main | gh token | XS | R10 remote golden env differs (advisory only) | merge commit ancestor of origin/main; CI-003 success; GATE-001…005 PASS on main | HARNESS-VCS-004, HARNESS-CI-002, HARNESS-CI-003, HARNESS-GATE-001, HARNESS-GATE-002, HARNESS-GATE-003, HARNESS-GATE-004, HARNESS-GATE-005 | M4 migration gate | blocked | 0 | gate closed: HARNESS-CI-002 cannot pass while Actions fail at startup (operator: RM-B-002) and HARNESS-VCS-003 awaits approval |  | no | main is the migration target for every consumer. | tag, ADR-0007 'implemented' wording, ledger 'ci-verified'
RM-A-003 | A Verification & Evidence | EP-3 Evidence over assertion | M5 | `listening-review.json` (schema audioforge.listening-review/1) with 7 judgments, committed under evidence/T5 and cited by the ledger; `listening_status` updated | A person opens the generated index.html at a matched level, judges all seven cases blind, downloads the JSON. Record the commit SHA and the acceptance manifest hashes reviewed. | listening_status: not_reviewed; page generated; no listener | HARNESS-ACC-003 PASS | P1 | RM-C-001 (a SHA to cite); RM-A-001 (page generation in the runner) | hard on C-001 | RM-C-006 unless waived | yes | dependent | no (waivable) | listener | any machine with a browser and monitoring | headphones/speakers at a known level | none | none | S | R9 no listener available | 7 non-null judgments; file cites SHA and spec_hashes; ledger row updated | HARNESS-ACC-003 | M5 release gate (waivable per harness §6.3) | blocked | 0 | operator: a listener must judge the seven cases (index.html in evidence/T2/work is regenerable via the runner) and export listening-review.json | Decision D3: blocking vs waivable; recommended waivable with expiry at 3.1.0. | no | The ledger separates numerical correctness from listening; only a human can supply the second. | the ledger may report a listening result
RM-A-005 | A Verification & Evidence | EP-3 Evidence over assertion | M5 | Rollback runbook section in docs/MIGRATION_3.md (checkout engine-2.16.0, run its canonical gate `scripts/run_tests.sh` with a python3 shim) and the RB-002 runner step | T0 showed the tag predates the Makefile, its runner hardcodes python3, its freshness guard needs the gitignored libraries/ tree, and its current.txt snapshot test is locale-dependent; the procedure must say all four. | Rehearsed at T0: 395 pass, 2 fail because the 2.16.0 freshness guard needs gitignored libraries/; with it linked one locale-dependent snapshot failure remains (harness §4.4); undocumented | HARNESS-RB-002 PASS from the runner (libraries linked, known snapshot failure documented or excluded); runbook present | P2 | RM-A-001 | hard | RM-C-006 | yes | dependent | no | maintainer | reference | — | push | none | S | none | RB-001 and RB-002 PASS; MIGRATION_3.md has a 'Rolling back' section | HARNESS-RB-001, HARNESS-RB-002 | M5 | complete | 100 | commit 41a153f (runbook in MIGRATION_3.md); evidence/T2 HARNESS-RB-001/002 |  | no | A rollback nobody has rehearsed is a hope. | release gate
RM-E-005 | E Contract Hardening | EP-5 Inspectable contract | M5 | Resampler cost curve documented in docs/MIGRATION_3.md (≈1.4× at unity, ≈2.7× at +12, ≈5× at +24 semitones vs 2.16.0) and a budget test with generous thresholds | The anti-alias kernel widens with playback rate; correct, but the migration guide does not mention the cost. | PERF-002 PARTIAL (numbers within budget, undocumented) | PASS | P2 | — | — | RM-C-006 (M5 gate) | yes | independent | no | maintainer | reference | — | push | none | S | R5 long sampled renders slower | PERF-002 PASS | HARNESS-PERF-002 | M5 performance gate | complete | 100 | commit 41a153f; evidence/T2 HARNESS-PERF-002 | Optimisation (e.g. polyphase or cached kernels) is out of scope; documenting is in. | no | A 5× cost is a behaviour change users will meet. | —
RM-C-006 | C Integration & Release | EP-1 Ship engine 3.0.0 | M6 | Tags `engine-3.0.0` and `dsl-2.0` on origin; GitHub release notes; final harness run committed under docs/evolution/evidence/T6 | Tag the merge commit after the M5 gate (listening evidence or waiver, PERF-002, RB-002). | Latest tags engine-2.16.0 / dsl-1.9 (2026-06-12) | HARNESS-REL-003 PASS; all non-waived rows PASS | P0 | RM-C-005, RM-C-004, RM-A-003 (or waiver), RM-E-005, RM-A-005, RM-D-003 | hard (gate M5) | — | no | dependent | yes | maintainer | GitHub | — | push tags, create release | gh token | XS | R9 listening never happens (waiver path exists) | harness §7 items 1–7 hold | HARNESS-REL-003, HARNESS-REL-001 | M6 release gate | blocked | 0 | depends on RM-C-005 and the M5 gate (listening review or waiver) | Completion is demonstrated by the harness, not declared. | no | A release is the only state in which the ledger may say 'released'. | —

## Dependencies
Depends on (from) | Item (to) | Type | Why the dependency exists | From (short) | To (short)
RM-C-001 | RM-C-002 | hard | The lockfile change must land on the release branch after the version bump commit exists. | Release branch `release/engine-3.0.0` with the repair commit | `uv.lock` regenerated and committed
RM-C-001 | RM-C-003 | hard | A review needs a branch and a PR to review. | Release branch `release/engine-3.0.0` with the repair commit | Pull request with an independent approving review; every fin
RM-C-001 | RM-C-004 | sequencing | Changelog edits belong on the release branch. | Release branch `release/engine-3.0.0` with the repair commit | `CHANGELOG.md` with one dated `[3.0.0]` section containing T
RM-C-001 | RM-A-003 | hard | The listening review must cite the commit SHA whose audio was judged. | Release branch `release/engine-3.0.0` with the repair commit | `listening-review.json` (schema audioforge.listening-review/
RM-C-001 | RM-A-002 | sequencing | The assessment is committed alongside the repair on the same branch. | Release branch `release/engine-3.0.0` with the repair commit | `docs/evolution/{report.md,roadmap.xlsx,harness.md}` committ
RM-C-001 | RM-D-001 | sequencing | Registry items reference commits and tests that must exist in history. | Release branch `release/engine-3.0.0` with the repair commit | Backlog registry items for the musical-correctness release (
RM-C-001 | RM-F-001 | hard | A ledger row cannot advance past 'independently-reproduced' without a commit. | Release branch `release/engine-3.0.0` with the repair commit | Ledger row A1: Instrument gain applied exactly once, includi
RM-B-001 | RM-B-003 | hard | The 3.10 matrix leg cannot pass before the import fix. | Package and tests import on Python 3.10: `datetime.UTC` → `t | Local matrix run recorded: `make check` under 3.10, 3.11, 3.
RM-B-001 | RM-B-004 | hard | A Python-floor smoke in the gate would fail until the fix lands. | Package and tests import on Python 3.10: `datetime.UTC` → `t | `make check` gains `uv lock --check` and a Python-floor impo
RM-C-002 | RM-B-004 | hard | `uv lock --check` in the gate would fail until the lockfile is regenerated. | `uv.lock` regenerated and committed | `make check` gains `uv lock --check` and a Python-floor impo
RM-B-001 | RM-C-005 | hard | CI-002 (green matrix) is a merge precondition and cannot be green on 3.10 without the fix. | Package and tests import on Python 3.10: `datetime.UTC` → `t | Release branch merged into `main` with the `ci` workflow gre
RM-B-002 | RM-C-005 | hard | Merge requires remote evidence; no job executes until the startup failure is fixed. | Root cause of `startup_failure` on every GitHub Actions run | Release branch merged into `main` with the `ci` workflow gre
RM-C-003 | RM-C-005 | hard | Review gate. | Pull request with an independent approving review; every fin | Release branch merged into `main` with the `ci` workflow gre
RM-E-001 | RM-E-002 | hard | A code field is only useful once every emitted code is registered. | `ambiguous_harmony`, `unrecognized_harmony`, `loop_boundary_ | `Diagnostic.code` field populated by compiler, validator, pl
RM-E-001 | RM-C-005 | hard | M2 contract gate (CON-001). | `ambiguous_harmony`, `unrecognized_harmony`, `loop_boundary_ | Release branch merged into `main` with the `ci` workflow gre
RM-E-003 | RM-C-005 | hard | M2 contract gate (CON-003). | `audioforge verify` accepts `.af` (compiles first) or return | Release branch merged into `main` with the `ci` workflow gre
RM-E-004 | RM-C-005 | hard | M2 contract gate (CON-004). | `validate_spec` (or the SDK/agent facade) copies on entry so | Release branch merged into `main` with the `ci` workflow gre
RM-D-004 | RM-C-005 | hard | M2 contract gate (GOV-004, GOV-006): ADRs must not contradict the merged code. | ADR-0001 amended: randomness is rooted in `performance_hash( | Release branch merged into `main` with the `ci` workflow gre
RM-D-005 | RM-C-005 | hard | M2 contract gate (GOV-005). | docs/index.md determinism sentence matches README and ADR-00 | Release branch merged into `main` with the `ci` workflow gre
RM-D-001 | RM-C-005 | hard | M3 contract gate (GOV-001). | Backlog registry items for the musical-correctness release ( | Release branch merged into `main` with the `ci` workflow gre
RM-D-002 | RM-C-005 | hard | M3 contract gate (GOV-002). | BL-004, BL-010, BL-011, BL-012, BL-013, BL-014 set to `done` | Release branch merged into `main` with the `ci` workflow gre
RM-D-003 | RM-C-005 | hard | M3 contract gate (GOV-003). | Ledger `Status` column uses the staged vocabulary (implement | Release branch merged into `main` with the `ci` workflow gre
RM-E-002 | RM-C-005 | decision | M3 architecture gate: CON-002 PASS or ADR-0008 records deferral with a waiver. | `Diagnostic.code` field populated by compiler, validator, pl | Release branch merged into `main` with the `ci` workflow gre
RM-C-005 | RM-C-006 | hard | Tags point at a merged commit with CI green. | Release branch merged into `main` with the `ci` workflow gre | Tags `engine-3.0.0` and `dsl-2.0` on origin; GitHub release
RM-C-004 | RM-C-006 | hard | A tag without a consolidated changelog ships an incoherent release message. | `CHANGELOG.md` with one dated `[3.0.0]` section containing T | Tags `engine-3.0.0` and `dsl-2.0` on origin; GitHub release
RM-A-003 | RM-C-006 | waivable | M5 release gate: listening evidence or a recorded waiver. | `listening-review.json` (schema audioforge.listening-review/ | Tags `engine-3.0.0` and `dsl-2.0` on origin; GitHub release
RM-E-005 | RM-C-006 | hard | M5 performance gate. | Resampler cost curve documented in docs/MIGRATION_3.md (≈1.4 | Tags `engine-3.0.0` and `dsl-2.0` on origin; GitHub release
RM-A-005 | RM-C-006 | hard | M5: rollback rehearsed before the release exists. | Rollback runbook section in docs/MIGRATION_3.md (checkout en | Tags `engine-3.0.0` and `dsl-2.0` on origin; GitHub release
RM-D-003 | RM-C-006 | hard | Ledger statuses read 'released' only at T6. | Ledger `Status` column uses the staged vocabulary (implement | Tags `engine-3.0.0` and `dsl-2.0` on origin; GitHub release
RM-A-001 | RM-A-002 | soft | The evidence directory convention comes from the runner. | `scripts/harness.sh` (from harness.md §8) plus `docs/evoluti | `docs/evolution/{report.md,roadmap.xlsx,harness.md}` committ
RM-A-001 | RM-A-004 | hard | ACC-004 is a runner step. | `scripts/harness.sh` (from harness.md §8) plus `docs/evoluti | Acceptance-bundle reproducibility check in the runner (two r
RM-A-001 | RM-A-005 | hard | RB-002 is a runner step. | `scripts/harness.sh` (from harness.md §8) plus `docs/evoluti | Rollback runbook section in docs/MIGRATION_3.md (checkout en
RM-C-005 | RM-F-001 | hard | 'ci-verified' status requires the merge. | Release branch merged into `main` with the `ci` workflow gre | Ledger row A1: Instrument gain applied exactly once, includi
RM-C-006 | RM-F-001 | hard | 'released' status requires the tag. | Tags `engine-3.0.0` and `dsl-2.0` on origin; GitHub release | Ledger row A1: Instrument gain applied exactly once, includi

## Milestones
Milestone | Checkpoint | Name | Objective | Entry criteria | Exit gate (harness rows that must be PASS) | Unlocks | Status
M0 | T0 | Current-state baseline | Measure the working tree with the harness before any change | — | All 59 assertions executed and recorded (harness.md §4) | M1 | complete (2026-09-05)
M1 | T1 | Foundation | Make the repair safe and the toolchain honest: commit + push, lockfile, Python 3.10, harness runner, CI root cause | M0 recorded | HARNESS-VCS-001, VCS-002, REL-004, PORT-001, OBS-002, GATE-006, SEC-002 = PASS; CI-001 diagnosed with owner | M2 | complete: evidence/T1 (7 PASS; CI-001 FAIL diagnosed, operator)
M2 | T2 | Core capabilities on a commit | Re-prove every functional assertion against a commit SHA, and land the small contract and record fixes | M1 gate open | AUD-*, MUS-*, ACC-001/002/004, GATE-001…005, PORT-002…004, MIG-*, RB-001, OBS-001, PERF-001, CON-001, CON-003, CON-004, GOV-004…007 = PASS on the branch head | M3 | complete: evidence/T2 (49+1 PASS on 4157c74; 7 operator-gated FAIL; 2 MANUAL)
M3 | T3 | Integration | First remote CI execution ever; independent review; registry and ledger know the work; structured diagnostics decision recorded | M2 gate open | CI-001, CI-002, CI-004, VCS-003, GOV-001…003, GOV-008, CON-002 (or ADR-0008 deferral + waiver) = PASS | M4 | in-progress: GOV-001…003, CON-002 PASS on the branch; CI-001/002/004 blocked on the Actions startup failure (operator); VCS-003 awaits an approving review (operator)
M4 | T4 | Migration (merge and consolidate) | Merge to main with CI green; one coherent 3.0.0 changelog; ADR-0007 may now say implemented | M3 gate open | VCS-004, CI-003, REL-002 = PASS; GATE-001…005 re-run on main | M5 | blocked (M3 gate)
M5 | T5 | Hardening | Human listening evidence, documented resampler cost, rollback rehearsed, offline run | M4 gate open | ACC-003 (or waiver), PERF-002, RB-002, SEC-001 = PASS | M6 | blocked (M4 gate); PERF-002, RB-002, SEC-001 already PASS on the branch; ACC-003 needs a listener
M6 | T6 | Desired state | Tags pushed; every non-waived assertion green; final evidence bundle committed; ledger reads released | M5 gate open | REL-003, REL-001 on the tag; zero unexplained FAIL; zero BLOCKED; final harness run committed | — | blocked (M5 gate)

## Harness Coverage
Harness ID | Category | Requirement (short) | Mode | T0 result | T0 detail | Target | Roadmap items | Green by
HARNESS-AUD-001 | AUD | A1: instrument layer gain is applied once, including virtual sections, measured through the full renderer on a pinned sample library | A | PASS | PASS | PASS | RM-F-001 | T2 (branch), T3 (CI)
HARNESS-AUD-002 | AUD | A2: note duration is gate time; release starts at note-off for synth and sampler, including note-off during attack and sustain-loop exit into the recorded tail | A | PASS | PASS | PASS | RM-F-002 | T2, T3
HARNESS-AUD-003 | AUD | A3: transposition and rate conversion suppress out-of-band content, preserve in-band pitch and level, including variable-rate glides | A | PASS | PASS | PASS | RM-F-003 | T2, T3
HARNESS-AUD-004 | AUD | A4: default mastering preserves absolute level below the ceiling; `normalize: peak` is explicit and round-trips; ceiling includes intersample peaks and delivered fades; LUFS path n | A | PASS | PASS | PASS | RM-F-004 | T2, T3
HARNESS-MUS-001 | MUS | M1: chord root and quality resolve across inversions; sevenths preserved; ambiguous (C6/Am7) and unrecognised clusters are preserved and reported; extensions follow key at onset; v | A | PASS | PASS | PASS | RM-F-005 | T2, T3
HARNESS-MUS-002 | MUS | M2: phrases use authored form and slurs; no fabricated cadence or pitch peak; cadence candidates need resolved roots, declared key and a downbeat; chord tones share onset under hum | A | PASS | PASS | PASS | RM-F-006 | T2, T3
HARNESS-MUS-003 | MUS | M3: technique fidelity is explicit (`technique_render.fidelity`), survives IR and plan, and `routing: fallbacks=forbid` rejects approximations; legato joins only contiguous monopho | A | PASS | PASS | PASS | RM-F-007 | T2, T3
HARNESS-MUS-004 | MUS | M4: `repeat` executes in the render contract (notes, duration, continuation, tempo, holds, markers, shaped automation, unique IDs, decompile round trip); meter/pickup define groove | A | PASS | PASS | PASS | RM-F-008 | T2, T3
HARNESS-MUS-005 | MUS | M5: gain, pan, metadata and reordering edits leave unrelated stems byte-identical; explicit `performance_seed` changes the take reproducibly; inserting an earlier note preserves la | A | PASS | PASS | PASS | RM-F-009 | T2, T3
HARNESS-MUS-006 | MUS | M6: analysis reports observations always and recommendations only under declared expectations; authored rests are not dead air | A | PASS | PASS | PASS | RM-F-010 | T2, T3
HARNESS-ACC-001 | ACC | The seven measured acceptance cases (seventh, phrase, repeat, release, quiet, alias, sample_gain) pass on the tree under test | A | PASS | PASS (11.2 s) | PASS | RM-F-001, RM-F-002, RM-F-003, RM-F-004, RM-F-005, RM-F-006, RM-F-008 | T2, T3
HARNESS-ACC-002 | ACC | The same cases expose the targeted defect on the previous engine, proving the assertions discriminate | A | PASS | PASS | PASS | RM-A-001 | T2
HARNESS-ACC-003 | ACC | A human listening review of the corpus is recorded and cited by the ledger; `listening_status` is no longer `not_reviewed` | M | FAIL | FAIL (no listener yet; page generated, status `not_reviewed`) | PASS | RM-A-003 | T5 (waivable, §6.3)
HARNESS-ACC-004 | ACC | The acceptance bundle is itself reproducible | A | PASS | PASS | PASS | RM-A-004 | T2
HARNESS-GATE-001 | GATE | The composed local gate passes in the reference environment | A | PASS | PASS: 884 passed, 2 skipped, 6 warnings; 2 min 36 s wall | PASS | RM-C-005, RM-F-011 | T2, and at every later checkpoint
HARNESS-GATE-002 | GATE | Statement coverage meets the repository threshold | A | PASS | PASS: 90.96 % (12 035 statements, 1 088 missed); new modules: arrangement 85.1 %, harmony 97.0 %, performance 96.3 %, musical_acceptance 85.6 % | PASS | RM-C-005, RM-F-011 | T2
HARNESS-GATE-003 | GATE | Golden corpus reproduces byte-for-byte in the lock's numeric environment | A | PASS | PASS | PASS | RM-C-005, RM-E-004, RM-F-011 | T2
HARNESS-GATE-004 | GATE | The documentation site builds strictly with the new pages in nav | A | PASS | PASS (exit 0, 0.25 s) | PASS | RM-C-005, RM-D-005, RM-F-011 | T2
HARNESS-GATE-005 | GATE | The backlog registry validates | A | PASS | PASS: "31 item(s) verified" | PASS | RM-C-005, RM-D-001, RM-F-011 | T2
HARNESS-GATE-006 | GATE | No whitespace errors in the diff | A | PASS | PASS | PASS | RM-A-001 | T1
HARNESS-PORT-001 | PORT | `make check` passes under Python 3.10 | A | FAIL | FAIL: `manifest-check` aborts, `ImportError: cannot import name 'UTC' from 'datetime'` in `audioforge/sample_catalog/licenses.py:6` (pre-existing since commit `f1c34a0`); `tests/test_lark_parser.py:9` | PASS | RM-B-001, RM-B-003, RM-B-004 | T1
HARNESS-PORT-002 | PORT | `make check` passes under Python 3.11 | A | PASS | PASS: 884 passed, 2 skipped, 1 min 46 s; numpy 2.4.6, scipy 1.17.1; goldens 5/5 with `env match: False` | PASS | RM-B-003 | T2
HARNESS-PORT-003 | PORT | `make check` passes under Python 3.12 | A | PASS | PASS: 884 passed, 2 skipped, 2 min 55 s; numpy 2.5.2, scipy 1.18.1 | PASS | RM-B-003 | T2
HARNESS-PORT-004 | PORT | Cross-environment golden behaviour is the documented one: advisory when `numeric_env` differs, strict when it matches | A | PASS | PASS: under numpy 2.5.2 the 5 goldens still reproduced byte-for-byte with `env match: False` | PASS | RM-B-003 | T2
HARNESS-CI-001 | CI | A GitHub Actions run for this repository executes at least one job | A | FAIL | FAIL: 7 of 7 runs since 2026-07-04 are `startup_failure`, 0 jobs, 0 s; both workflow YAML files parse; Actions enabled (`allowed_actions: all`); repo private; billing endpoint needs the `user` token s | PASS | RM-B-002 | T1 diagnosed, T3 PASS
HARNESS-CI-002 | CI | The `ci` workflow is green on the release branch head for Python 3.10, 3.11 and 3.12 | A | FAIL | FAIL (no run has ever executed) | PASS | RM-B-001, RM-B-002, RM-C-005 | T3
HARNESS-CI-003 | CI | The `ci` workflow is green on `main` after the merge | A | FAIL | FAIL | PASS | RM-C-005 | T4
HARNESS-CI-004 | CI | The `backlog-governance` workflow is green | A | FAIL | FAIL (`startup_failure`) | PASS | RM-B-002, RM-D-001 | T3
HARNESS-VCS-001 | VCS | The repair is committed; the tree under test is clean | A | FAIL | FAIL: 45 modified (+1 605/−609) and 12 untracked files | PASS | RM-C-001 | T1
HARNESS-VCS-002 | VCS | A second copy exists: the tree is clean and the release branch is pushed and equals local | A | FAIL | FAIL: `origin` last pushed 2026-07-05; local `main` = `origin/main` = `60c0fd5`, so the repair has never left this machine | PASS | RM-C-001 | T1
HARNESS-VCS-003 | VCS | The repair was reviewed by someone other than its author and findings were closed | A+M | FAIL | FAIL (no branch, no PR) | PASS | RM-C-003 | T3
HARNESS-VCS-004 | VCS | The tree is clean and the release commit is an ancestor of `origin/main` | A | FAIL | FAIL | PASS | RM-C-005 | T4
HARNESS-REL-001 | REL | Every version literal equals `audioforge/version.py` | A | PASS | PASS (3.0.0 / DSL 2.0 everywhere the tool manages) | PASS | RM-C-004, RM-C-006, RM-F-011 | T1
HARNESS-REL-002 | REL | `CHANGELOG.md` describes one release: the `[3.0.0]` section carries a date and contains both the Track E infrastructure (AF-R01…R13, committed since 2.16.0) and the musical fixes; | A | FAIL | FAIL: Track E sits under `[Unreleased]` while `[3.0.0]` lists only the fixes; no date | PASS | RM-C-004 | T4
HARNESS-REL-003 | REL | Tags `engine-3.0.0` and `dsl-2.0` exist on `origin` and point at an ancestor of `main` | A | FAIL | FAIL (latest tags: `engine-2.16.0`, `dsl-1.9` at `282756e`, 2026-06-12) | PASS | RM-C-006 | T6
HARNESS-REL-004 | REL | The `uv` lockfile matches `pyproject.toml` | A | FAIL | FAIL: "The lockfile at `uv.lock` needs to be updated" (still records `audioforge 2.16.0`) | PASS | RM-B-004, RM-C-002 | T1
HARNESS-GOV-001 | GOV | The musical-correctness work is registered in the backlog system of record with evidence checks | A | FAIL | FAIL: no item mentions the repair, ADR-0007, 3.0.0 or any ledger row | PASS | RM-D-001 | T3
HARNESS-GOV-002 | GOV | Registry status agrees with git history for Track E | A | FAIL | FAIL: all six are `ready` although AF-R03, R09, R10, R11, R12, R13 are in `git log` | PASS | RM-D-002 | T3
HARNESS-GOV-003 | GOV | The ledger uses the staged status vocabulary and cites harness IDs; no row says `Verified` for uncommitted or un-CI'd work | A | FAIL | FAIL: 12 rows read `Verified` on self-reported local evidence | PASS | RM-D-003 | T3 (statuses advance at each later checkpoint)
HARNESS-GOV-004 | GOV | ADR-0001 no longer states that randomness is rooted in the spec hash without pointing to ADR-0007 | A | FAIL | FAIL: ADR-0001 says "All randomness derives from per-component seeds rooted in the spec hash"; the code now roots it in `performance_hash(seed, variant)` | PASS | RM-D-004 | T2
HARNESS-GOV-005 | GOV | The docs-site home page makes the same determinism claim as README and ADR-0007 | A | FAIL | FAIL: `docs/index.md:14` still promises "byte-identical audio, every render, forever" | PASS | RM-D-005 | T2
HARNESS-GOV-006 | GOV | ADR-0007 status reflects delivery state: "Implemented" only when `HARNESS-VCS-004` and `HARNESS-CI-003` pass | A | FAIL | FAIL: status reads "Accepted and implemented" for uncommitted code | PASS | RM-D-004 | T2 (wording), T4 (final)
HARNESS-GOV-007 | GOV | The coordination pointer `.agent-tasks/.current_task` names an active task or is absent | A | FAIL | FAIL: points at `task-1783257140897-7b8a`, archived with status `failed` | PASS | RM-D-006 | T2 (non-blocking)
HARNESS-GOV-008 | GOV | Ledger evidence citations are accurate: every cited test file was changed by the repair or is labelled a pre-existing regression guard | M | PARTIAL | PARTIAL: `tests/test_performance_model.py` is cited for M2, M3 and A2 but is unchanged (its five tests are regression guards, not new assertions) | PASS | RM-D-003 | T3 (non-blocking)
HARNESS-CON-001 | CON | Every diagnostic code the engine emits is in `capability_manifest()["diagnostic_codes"]` and therefore in `docs/DIAGNOSTIC_CODES.md` | A | FAIL | FAIL: registry has 29 codes; `ambiguous_harmony`, `unrecognized_harmony`, `loop_boundary_tail` and all analysis codes are absent (`render_plan_approximation` is present) | PASS | RM-E-001 | T2
HARNESS-CON-002 | CON | `Diagnostic` carries a machine-readable `code`, exposed through `agent_tools` and MCP envelopes | A | FAIL | FAIL: `Diagnostic(severity, message, path)`; codes are embedded in message text | PASS | RM-E-002 | T3
HARNESS-CON-003 | CON | `audioforge verify` given a non-JSON spec returns a structured diagnostic, not a raw decoder error | A | FAIL | FAIL: prints `Error: Expecting value: line 1 column 1 (char 0)`, exit 1 | PASS | RM-E-003 | T2
HARNESS-CON-004 | CON | `validate_spec` and `run_tool("validate", …)` do not mutate the caller's spec | A | FAIL | FAIL: `validate_spec` returns the same object and rewrites it in place (duration 2.0 → 4.0, repeats consumed); `run_tool("validate")` mutates the caller's dict too | PASS | RM-E-004 | T2
HARNESS-PERF-001 | PERF | The composed gate stays inside a five-minute budget | A | PASS | PASS: 156 s | PASS | RM-A-001, RM-B-004 | every checkpoint
HARNESS-PERF-002 | PERF | The anti-alias resampler's cost is bounded and documented | A | PARTIAL | PARTIAL: measured 57 / 110 / 204 ms (engine 2.16.0: 41 / 42 / 41 ms, so up to 5× at two octaves up); the cost is undocumented | PASS | RM-E-005 | T5
HARNESS-MIG-001 | MIG | A 2.16.0 manifest verified by 3.0.0 fails loudly and non-zero, as ADR-0007 intends | A | PASS | PASS | PASS | RM-F-011 | T2
HARNESS-MIG-002 | MIG | Every `.af` in the repository compiles and renders under 3.0.0 without error diagnostics | A | PASS | PASS (1 sample + 5 goldens) | PASS | RM-F-011 | T2
HARNESS-MIG-003 | MIG | Structural IR migration flags that audio review is required | A | PASS | PASS | PASS | RM-F-011 | T2
HARNESS-RB-001 | RB | A rollback anchor exists and is runnable: the previous release tag exports and renders the acceptance corpus with its documented behaviour | A | PASS | PASS (`282756e`; baseline metrics recorded in §4) | PASS | RM-A-005 | T2
HARNESS-RB-002 | RB | Rollback rehearsal: the previous release's own gate passes in an isolated export with the current toolchain | A | PARTIAL | PARTIAL: 395 passed, 2 failed, 2 skipped; both failures are `tests/test_catalog_freshness.py` asserting that gitignored `libraries/` exists; with `libraries/` linked one remains (`test_current_txt_mat | PASS | RM-A-005 | T5
HARNESS-OBS-001 | OBS | Render manifests identify both the contract and the take | A | PASS | PASS | PASS | RM-F-009 | T2
HARNESS-OBS-002 | OBS | Each checkpoint leaves a durable evidence bundle in the repository | A | PARTIAL | PARTIAL: T0 evidence exists only in the session scratch directory; load-bearing lines are transcribed in §4 | PASS | RM-A-001, RM-A-002 | T1
HARNESS-SEC-001 | SEC | The test suite and the acceptance tool run without network access | A | BLOCKED | BLOCKED: not executed at T0 (needs an isolation run; sample-catalog network paths are mocked in tests, but that is inferred, not proven) | PASS | RM-A-001 | T5 (non-blocking)
HARNESS-SEC-002 | SEC | No credentials in tracked files | A | PASS | PASS (0) | PASS | RM-A-001 | T1

## Risks
ID | Category | Risk | Likelihood | Impact | Mitigation / owner item | Harness signal | Status
R1 | data | Loss of the uncommitted repair (single copy on one machine) | high | critical | RM-C-001 on Day 1; harness VCS-001/002 | HARNESS-VCS-001, HARNESS-VCS-002 | open
R2 | operational | CI startup failure is a billing/spending-limit condition on a private repository; the remedy may cost money or require a self-hosted runner | medium | high | RM-B-002; decision D4; interim: local matrix (RM-B-003) is the only gate | HARNESS-CI-001 | open (cause unconfirmed)
R3 | implementation | Further Python 3.10 incompatibilities appear after the two known ones | low | medium | RM-B-003 runs the full gate on 3.10 | HARNESS-PORT-001 | open
R4 | migration | Existing .af specs and compositions render differently (gain, tails, spectra, repeats, takes) after 3.0.0 | certain | medium | MIGRATION_3.md; MIG-001 proves the loud MISMATCH; changelog consolidation (RM-C-004); release notes | HARNESS-MIG-001, HARNESS-REL-002 | accepted (intended)
R5 | performance | Anti-alias resampler is ≈2.7× slower at +12 and ≈5× at +24 semitones; long sampled orchestral renders get slower | medium | medium | RM-E-005 documents and bounds it; optimisation deferred and out of scope | HARNESS-PERF-002 | open
R6 | architecture | validate_spec / run_tool('validate') mutate the caller's spec when repeats are present; agents may render or hash a spec they did not author | medium | medium | RM-E-004; decision D2 | HARNESS-CON-004 | open
R7 | architecture | Diagnostics are prose with embedded codes; three new codes unregistered; agents must parse text | high | medium | RM-E-001, RM-E-002; decision D1 | HARNESS-CON-001, HARNESS-CON-002 | open
R8 | architecture | ADR-0001 and ADR-0007 disagree on where randomness is rooted; docs/index.md makes an obsolete absolute claim | certain | low | RM-D-004, RM-D-005 | HARNESS-GOV-004, HARNESS-GOV-005 | open
R9 | operational | No human listening review ever happens; the release can only claim numerical correctness | medium | medium | RM-A-003; waiver policy with expiry at 3.1.0 (decision D3) | HARNESS-ACC-003 | open
R10 | infrastructure | Remote CI runners have a different numeric environment; the golden gate is advisory there, so strict byte-identity is proven only locally | medium | medium | T0 evidence: goldens byte-identical across numpy 2.4.6/2.5.2 and Python 3.11–3.13 on x86_64; AF-R16 (out of scope) for cross-platform | HARNESS-PORT-004, HARNESS-CI-003 | accepted
R11 | governance | Registry statuses lag delivery (six Track E items 'ready' though delivered); readers stop trusting the system of record | certain | low | RM-D-002; RM-D-001 | HARNESS-GOV-002, HARNESS-GOV-001 | open
R12 | operational | Single maintainer; independent review requires a second person or an agent session with human sign-off | high | medium | RM-C-003 owner = reviewer; reviews may be agent-assisted but signed by a human | HARNESS-VCS-003 | open
R13 | implementation | Adding code paths (Diagnostic.code, gate targets) drops coverage below 90.1 or pushes make check past 300 s | low | low | GATE-002, PERF-001 at every checkpoint | HARNESS-GATE-002, HARNESS-PERF-001 | open
R14 | operational | backlog-governance workflow also fails at startup, so registry edits are validated only locally until RM-B-002 | high | low | node script locally (GATE-005); RM-B-002 | HARNESS-CI-004 | open
R15 | security | Sample-catalog code paths reach the network; offline property of the suite is inferred from mocks, not proven | low | low | SEC-001 isolation run (non-blocking) | HARNESS-SEC-001 | open
R16 | operational | Concurrent agents edit the same files during the release work | low | medium | .agent-tasks protocol (registry + locks); RM-D-006 hygiene | HARNESS-GOV-007 | open
R17 | scope | Track M/X work (tuning engine, pc-set operators, stochastic primitives) gets pulled into the release | medium | medium | Roadmap scope statement: only EP-1…EP-5; Track M/X stay in docs/backlog.yml | — | open
R19 | migration | The rollback target's own gate is not green in an isolated export: it needs the gitignored libraries/ tree and its current.txt snapshot test is locale-dependent, so an emergency rollback would show red tests unrelated to the engine | certain | low | RM-A-005 runbook: link libraries/, document the known snapshot failure | HARNESS-RB-002 | open
R18 | data | The git remote is the only off-machine copy; GitHub repo is private and Actions are down, so a lost token or account issue blocks recovery | low | high | RM-C-001 push; optionally a second remote (out of scope) | HARNESS-VCS-002 | open

## Resources
Kind | Resource | Needed by | Requirement | Availability at T0
Role | Maintainer (repository owner) | RM-C-*, RM-B-001, RM-B-003, RM-B-004, RM-A-*, RM-D-*, RM-E-* | write + push; runs the reference environment | present (Pedro Anisio Silva)
Role | Repository admin (billing/Actions) | RM-B-002 | GitHub Settings → Actions, Billing | present if the owner is the admin; otherwise to be identified
Role | Independent reviewer | RM-C-003 | PR review permission | to be identified (person, or agent + human sign-off)
Role | Listener | RM-A-003 | none | to be identified
Environment | Reference machine | all automated rows | Linux x86_64, 12 cores, ./.venv Python 3.13.12, numpy 2.4.6, scipy 1.17.1, cc, tree, node 24, uv 0.10.9, gh | present
Environment | Matrix venvs 3.10 / 3.11 / 3.12 | RM-B-001, RM-B-003 | uv-managed CPython; ~1 min to build each; network for wheels | present in the T0 scratch directory; re-creatable with uv
Environment | GitHub Actions ubuntu-latest | RM-C-005, HARNESS-CI-* | Actions minutes for a private repo (3 jobs × ≈3 min per push) | BLOCKED: startup_failure since 2026-07-04
Infrastructure | Git remote github.com/pedroanisio/audioforge (private) | RM-C-001, RM-C-005, RM-C-006 | push access | present
Infrastructure | Docs toolchain | HARNESS-GATE-004 | uv + mkdocs-material fetched ephemerally (network) | present
Permission | Push to origin / merge to main / create tags and releases | RM-C-001, RM-C-005, RM-C-006 | repo write/admin | present for the owner
Permission | Actions billing visibility | RM-B-002 | account-level | unknown
Credential | gh OAuth token (repo scope) | HARNESS-CI-*, HARNESS-VCS-003 | present | present; add `user` scope only if diagnosing billing via API
Credential | API keys | — | none required anywhere in this roadmap | n/a
External service | GitHub (Actions, PRs, releases) | RM-B-002, RM-C-003, RM-C-005, RM-C-006 | availability | Actions currently non-functional for this repo
External service | Network for uv/mkdocs/wheels | RM-B-003, HARNESS-GATE-004 | one-time fetches | present
Hardware | Monitoring headphones/speakers | RM-A-003 | matched playback level; blind A/B | to be arranged

## Traceability
Requirement ID | Report requirement (report.md §Desired state) | Roadmap items | Harness tests | Evidence | Milestone exit gate
REQ-1 | Audio semantics A1–A4 hold on the released engine | RM-F-001…004, RM-C-005, RM-C-006 | HARNESS-AUD-001…004, HARNESS-ACC-001/002/004 | pytest logs; acceptance manifest.json (metrics + output_sha256) | M2 test gate → M4 → M6
REQ-2 | Musical semantics M1–M6 hold on the released engine | RM-F-005…010 | HARNESS-MUS-001…006 | pytest logs; acceptance manifest | M2 → M4 → M6
REQ-3 | All surfaces agree (G1) | RM-F-011, RM-B-004 | HARNESS-GATE-001…005, HARNESS-REL-001, HARNESS-MIG-001…003 | make check log; coverage report; mkdocs log; governance output | M2 contract/test gates
REQ-4 | The repair is committed, duplicated, reviewed and merged | RM-C-001, RM-C-003, RM-C-005 | HARNESS-VCS-001…004 | git/gh output | M1 data-safety; M3 review; M4 migration
REQ-5 | CI executes and is green on the declared matrix | RM-B-001, RM-B-002, RM-B-003 | HARNESS-CI-001…004, HARNESS-PORT-001…004 | gh run JSON; matrix logs | M1 portability; M3 CI gate
REQ-6 | Release is tagged, locked and described coherently | RM-C-002, RM-C-004, RM-C-006 | HARNESS-REL-001…004 | git ls-remote; CHANGELOG; uv lock --check | M1; M4; M6 release gate
REQ-7 | Governance and architecture records describe the shipped system | RM-D-001…006 | HARNESS-GOV-001…008 | backlog.yml; ledger; ADR diffs | M2/M3 contract gates
REQ-8 | Diagnostics are structured; validation is pure | RM-E-001…004 | HARNESS-CON-001…004 | python checks; ADR-0008 | M2 contract gate; M3 architecture gate
REQ-9 | Performance is bounded and documented | RM-E-005 | HARNESS-PERF-001/002 | benchmark output; MIGRATION_3.md | M5 performance gate
REQ-10 | Rollback is proven | RM-A-005 | HARNESS-RB-001/002 | rollback gate log | M5
REQ-11 | Human listening evidence exists | RM-A-003 | HARNESS-ACC-003 | listening-review.json | M5 release gate (waivable)
REQ-12 | Progress is measured by execution and stored durably | RM-A-001, RM-A-002, RM-A-004 | HARNESS-OBS-001/002 | scripts/harness.sh; evidence/<T>/summary.tsv | every transition (observability gate)
REQ-13 | Offline and secret-free | RM-A-001 | HARNESS-SEC-001/002 | isolation run log; git grep | M5 security gate

## Decisions
ID | Decision | Recommended option | Alternative(s) | Roadmap item | Where it is decided
D1 | Ship `Diagnostic.code` in 3.0.0 or defer to 3.1? | Include in 3.0.0 (additive field; 3.0 is already a breaking release; agents are the primary consumer) | Defer with ADR-0008 + waiver; keeps 3.0.0 smaller | RM-E-002 | M3 architecture gate
D2 | Where to stop `validate_spec` from mutating callers | deepcopy at the top of validate_spec (one place, negligible next to rendering) | copy only at SDK/agent facade; or document mutation as intended | RM-E-004 | M2 contract gate
D3 | Is the human listening review release-blocking? | Waivable with a recorded waiver expiring at engine 3.1.0; the release notes must state 'not reviewed' | Blocking: no tag without a listener | RM-A-003 | M5 release gate
D4 | How to restore CI | Confirm and fix Actions billing/spending limit for the private repo | Self-hosted runner on the reference machine; or a different CI provider | RM-B-002 | M1/M3
D5 | Changelog shape | Fold Track E into a single dated [3.0.0] | Two sections (infrastructure vs semantics) under one version header | RM-C-004 | M4
D6 | Golden lock after semantic change | Accept the regenerated hashes (already done in the tree) and state in the changelog that 2.16 hashes are not evidence for 3.0 sound | Keep both locks side by side | RM-F-011 | M2
D7 | Ledger status vocabulary | Adopt the five-stage vocabulary from harness.md §1; advance statuses only from evidence bundles | Keep 'Verified' with a footnote | RM-D-003 | M3